## Stakeholder Register
Stakeholder Register
Northbridge Digital Banking Platform Upgrade · PRJ-2026-0147
ID | Stakeholder (role) | Org | RACI | What they need | Power | Interest | Engagement approach
SH-01 | VP Digital Banking (Sponsor) | Northbridge | A | Confidence the platform lands on time and on budget | High | High | Weekly 1:1; approves CRs >$25K; owns go/no-go
SH-02 | Head of Retail Banking (Business Owner) | Northbridge | A | Design sign-off; UAT acceptance | High | High | Design & UAT gates; monthly steering
SH-03 | IT Delivery Lead | Northbridge | R | Build progress; environment readiness | Medium | High | Daily stand-up; weekly delivery review
SH-04 | SI Partner Engagement Manager (Meridian) | Meridian SI | R | Clear scope; timely approvals; invoice sign-off | Medium | High | Weekly delivery call; monthly commercial review
SH-05 | Finance Business Partner | Northbridge | C | Accurate spend, accruals and forecast | Medium | High | Monthly cost review; validates EAC before steering
SH-06 | Risk & Compliance (OSFI B-13) | Northbridge | C | Evidence of technology-risk controls | High | Medium | Gate reviews at design and pre-go-live
SH-07 | Procurement | Northbridge | C | PO compliance; no invoices without a PO | Low | Medium | Ad-hoc; receives the PO-compliance exception log
SH-08 | PCO (Keshaav Gite) | Northbridge | R | Runs schedule, cost, RAID, reporting | — | — | Owns the governance cadence

## Budget
Approved Budget — by cost category by month
Baselined 2026-01-15. Figures in CAD. Total BAC $1,260,000.
Cost Category | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total Budget
SI Partner Fees | 12600 | 21000 | 33600 | 42000 | 50400 | 50400 | 50400 | 46200 | 42000 | 37800 | 21000 | 12600 | 420000
Internal Labour | 15600 | 18200 | 20800 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 23400 | 20800 | 20800 | 260000
Contractor Labour | 3600 | 7200 | 14400 | 21600 | 25200 | 25200 | 25200 | 21600 | 18000 | 10800 | 5400 | 1800 | 180000
Software Licences | 43500 | 7250 | 7250 | 7250 | 7250 | 7250 | 7250 | 7250 | 7250 | 14500 | 14500 | 14500 | 145000
Hardware & Infra | 4500 | 18000 | 27000 | 18000 | 9000 | 4500 | 2700 | 1800 | 1800 | 900 | 900 | 900 | 90000
Cloud / Hosting | 1200 | 2400 | 3600 | 4800 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 60000
Training & Change | 0 | 0 | 0 | 500 | 1250 | 2000 | 2500 | 3750 | 6250 | 6250 | 1750 | 750 | 25000
Travel | 1200 | 1200 | 1200 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 840 | 840 | 12000
Contingency | 3400 | 3400 | 5440 | 5440 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 4760 | 4760 | 68000
TOTAL | 85600 | 78650 | 113290 | 123950 | 130260 | 126510 | 125210 | 117760 | 112460 | 107410 | 75950 | 62950 | 1260000
Cumulative Plan | 85600 | 164250 | 277540 | 401490 | 531750 | 658260 | 783470 | 901230 | 1013690 | 1121100 | 1197050 | 1260000

## Actuals (D365 Export)
Actuals — Accounts Payable transaction export
Source: Dynamics 365 Finance · AP vendor transactions · exported 2026-09-01
Posting Date | Voucher | Vendor ID | Vendor Name | Invoice No | PO Ref | Cost Category | Description | Amount | Currency | Status
2026-04-19 | AP-500020 | V-10166 | Vantage Consulting Associates | INV-8819 | PO-2026-1032 | Contractor Labour | Senior developer - monthly | 14377.74 | CAD | Posted
2026-08-28 | GJ-500110 |  | (Internal journal) |  |  | Internal Labour | Internal labour recharge - monthly | 23548.67 | CAD | Posted
2026-07-17 | AP-500084 | V-10133 | Keystone Training Partners | INV-8883 | PO-2026-1017 | Training & Change | End-user training materials | 1378.95 | CAD | Posted
2026-01-24 | AP-500034 | V-10102 | Northgate Software Licensing | INV-8833 | PO-2026-1062 | Software Licences | API gateway licence | 12883.3 | CAD | Posted
2026-07-11 | AP-500028 | V-10078 | Ironwood Contracting Group | INV-8827 | PO-2026-1067 | Contractor Labour | Solution architect - part time | 14754.12 | CAD | Posted
2026-07-11 | AP-500099 | V-10150 | Harbourview Travel Management | INV-8898 | PO-2026-1010 | Travel | Vendor site visit | 460.75 | CAD | Posted
2026-03-13 | AP-500067 | V-10044 | Cascade Cloud Services Inc | INV-8866 | PO-2026-1035 | Cloud / Hosting | Compute - monthly usage | 2019.1 | CAD | Posted
2026-04-18 | AP-500094 | V-10150 | Harbourview Travel Management | INV-8893 | PO-2026-1028 | Travel | Vendor site visit | 438.8 | CAD | Posted
2026-04-12 | AP-500051 | V-10119 | Summit Hardware Solutions | INV-8850 | PO-2026-1020 | Hardware & Infra | Storage expansion | 6100.62 | CAD | Posted
2026-02-28 | GJ-500104 |  | (Internal journal) |  |  | Internal Labour | Internal labour recharge - monthly | 18171.13 | CAD | Posted
2026-07-25 | AP-500012 | V-10021 | Meridian Systems Integration Ltd | INV-8811 | PO-2026-1087 | SI Partner Fees | Sprint delivery - milestone billing | 26526.18 | CAD | Posted
2026-03-25 | AP-500006 | V-10021 | Meridian Systems Integration Ltd | INV-8805 | PO-2026-1054 | SI Partner Fees | Integration build - phase billing | 36944.61 | CAD | Posted
2026-07-28 | GJ-500109 |  | (Internal journal) |  |  | Internal Labour | Internal labour recharge - monthly | 23215.93 | CAD | Posted
2026-06-15 | AP-500098 | V-10150 | Harbourview Travel Management | INV-8897 | PO-2026-1041 | Travel | Onsite integration workshop | 297.49 | CAD | Posted
2026-05-20 | AP-500008 | V-10021 | Meridian Systems Integration Ltd | INV-8807 | PO-2026-1015 | SI Partner Fees | UAT support services | 25864.07 | CAD | Posted
2026-08-03 | AP-500102 | V-10150 | Harbourview Travel Management | INV-8901 | PO-2026-1079 | Travel | Onsite integration workshop | 449.64 | CAD | Posted
2026-05-14 | AP-500115 | V-10102 | Northgate Software Licensing | INV-8905 | PO-2026-1044 | Software Licences | US licence true-up (USD invoice) | 14900 | USD | Posted
2026-02-20 | AP-500004 | V-10021 | Meridian Systems Integration Ltd | INV-8803 | PO-2026-1025 | SI Partner Fees | Cutover support | 9118.08 | CAD | Posted
2026-06-10 | AP-500083 | V-10133 | Keystone Training Partners | INV-8882 | PO-2026-1022 | Training & Change | Change readiness workshops | 527.24 | CAD | Posted
2026-01-09 | AP-500016 | V-10166 | Vantage Consulting Associates | INV-8815 | PO-2026-1083 | Contractor Labour | Solution architect - part time | 4228.79 | CAD | Posted
2026-05-11 | AP-500054 | V-10119 | Summit Hardware Solutions | INV-8853 | PO-2026-1036 | Hardware & Infra | Network switch upgrade | 2242.85 | CAD | Posted
2026-08-26 | AP-500114 | V-10044 | Cascade Cloud Services Inc | INV-8904 | PO-2026-1014 | Cloud / Hosting | Awaiting approval | 5820 | CAD | Pending
2026-08-24 | AP-500029 | V-10166 | Vantage Consulting Associates | INV-8828 | PO-2026-1083 | Contractor Labour | Data migration specialist | 9561.23 | CAD | Posted
2026-06-11 | AP-500042 | V-10102 | Northgate Software Licensing | INV-8841 | PO-2026-1058 | Software Licences | Monitoring suite subscription | 7794 | CAD | Posted
2026-01-10 | AP-500032 | V-10102 | Northgate Software Licensing | INV-8831 | PO-2026-1008 | Software Licences | Core platform licence - annual | 13873.17 | CAD | Posted
2026-08-22 | AP-500062 | V-10119 | Summit Hardware Solutions | INV-8861 | PO-2026-1095 | Hardware & Infra | Network switch upgrade | 396.9 | CAD | Posted
2026-05-11 | AP-500053 | V-10119 | Summit Hardware Solutions | INV-8852 | PO-2026-1014 | Hardware & Infra | Application server refresh | 1936.31 | CAD | Posted
2026-05-10 | AP-500079 | V-10133 | Keystone Training Partners | INV-8878 | PO-2026-1025 | Training & Change | Super-user training cohort | 203.6 | CAD | Posted
2026-02-04 | AP-500065 | V-10044 | Cascade Cloud Services Inc | INV-8864 | PO-2026-1060 | Cloud / Hosting | Storage - monthly | 1249.07 | CAD | Posted
2026-06-06 | AP-500025 | V-10078 | Ironwood Contracting Group | INV-8824 | PO-2026-1046 | Contractor Labour | Data migration specialist | 9277.27 | CAD | Posted
2026-05-20 | AP-500009 | V-10021 | Meridian Systems Integration Ltd | INV-8808 | PO-2026-1037 | SI Partner Fees | Cutover support | 27884.56 | CAD | Posted
2026-05-28 | GJ-500107 |  | (Internal journal) |  |  | Internal Labour | Internal labour recharge - monthly | 23350.91 | CAD | Posted
2026-08-24 | AP-500014 | V-10021 | Meridian Systems Integration Ltd | INV-8813 | PO-2026-1041 | SI Partner Fees | Sprint delivery - milestone billing | 21772.4 | CAD | Posted
2026-02-09 | AP-500035 | V-10102 | Northgate Software Licensing | INV-8834 | PO-2026-1012 | Software Licences | Core platform licence - annual | 2603.16 | CAD | Posted
2026-01-10 | AP-500002 | V-10021 | Meridian Systems Integration Ltd | INV-8801 | PO-2026-1017 | SI Partner Fees | Sprint delivery - milestone billing | 14684.44 | CAD | Posted
2026-02-26 | AP-500037 | V-10102 | Northgate Software Licensing | INV-8836 | PO-2026-1006 | Software Licences | Core platform licence - annual | 2498.84 | CAD | Posted
2026-03-16 | AP-500039 | V-10102 | Northgate Software Licensing | INV-8838 | PO-2026-1023 | Software Licences | Monitoring suite subscription | 2924.58 | CAD | Posted
2026-07-25 | AP-500059 | V-10119 | Summit Hardware Solutions | INV-8858 | PO-2026-1019 | Hardware & Infra | Application server refresh | 1053.8 | CAD | Posted
2026-08-20 | AP-500085 | V-10133 | Keystone Training Partners | INV-8884 | PO-2026-1057 | Training & Change | Super-user training cohort | 651.5 | CAD | Posted
2026-02-14 | AP-500018 | V-10166 | Vantage Consulting Associates | INV-8817 | PO-2026-1028 | Contractor Labour | QA analyst - monthly | 4315.39 | CAD | Posted
2026-06-14 | AP-500072 | V-10044 | Cascade Cloud Services Inc | INV-8871 | PO-2026-1055 | Cloud / Hosting | Compute - monthly usage | 2440.58 | CAD | Posted
2026-03-27 | AP-500092 | V-10150 | Harbourview Travel Management | INV-8891 | PO-2026-1073 | Travel | Vendor site visit | 519.02 | CAD | Posted
2026-01-24 | AP-500047 | V-10119 | Summit Hardware Solutions | INV-8846 |  | Hardware & Infra | Load balancer appliance | 3280.91 | CAD | Posted
2026-07-20 | AP-500013 | V-10021 | Meridian Systems Integration Ltd | INV-8812 | PO-2026-1093 | SI Partner Fees | Design workshop facilitation | 28888.74 | CAD | Posted
2026-08-26 | AP-500113 | V-10078 | Ironwood Contracting Group | INV-8903 | PO-2026-1091 | Contractor Labour | Awaiting approval | 22400 | CAD | Pending
2026-06-17 | AP-500097 | V-10150 | Harbourview Travel Management | INV-8896 | PO-2026-1023 | Travel | Onsite integration workshop | 333.65 | CAD | Posted
2026-05-17 | AP-500081 | V-10133 | Keystone Training Partners | INV-8880 | PO-2026-1053 | Training & Change | Change readiness workshops | 239.87 | CAD | Posted
2026-05-19 | AP-500023 | V-10078 | Ironwood Contracting Group | INV-8822 | PO-2026-1013 | Contractor Labour | Data migration specialist | 17172.44 | CAD | Posted
2026-06-04 | AP-500026 | V-10078 | Ironwood Contracting Group | INV-8825 | PO-2026-1030 | Contractor Labour | Senior developer - monthly | 11904.54 | CAD | Posted
2026-07-04 | AP-500044 | V-10102 | Northgate Software Licensing | INV-8843 | PO-2026-1006 | Software Licences | Test automation licence | 2450.7 | CAD | Posted
2026-06-28 | GJ-500108 |  | (Internal journal) |  |  | Internal Labour | Internal labour recharge - monthly | 23057.77 | CAD | Posted
2026-03-09 | AP-500038 | V-10102 | Northgate Software Licensing | INV-8837 | PO-2026-1068 | Software Licences | Test automation licence | 3883.13 | CAD | Posted
2026-08-10 | AP-500031 | V-10078 | Ironwood Contracting Group | INV-8830 | PO-2026-1008 | Contractor Labour | Data migration specialist | 9414.38 | CAD | Posted
2026-03-28 | GJ-500105 |  | (Internal journal) |  |  | Internal Labour | Internal labour recharge - monthly | 20318.76 | CAD | Posted
2026-04-21 | AP-500069 | V-10044 | Cascade Cloud Services Inc | INV-8868 | PO-2026-1033 | Cloud / Hosting | Compute - monthly usage | 2876.33 | CAD | Posted
2026-08-19 | AP-500030 | V-10166 | Vantage Consulting Associates | INV-8829 | PO-2026-1057 | Contractor Labour | Senior developer - monthly | 9334.29 | CAD | Posted
2026-07-20 | AP-500058 | V-10119 | Summit Hardware Solutions | INV-8857 | PO-2026-1001 | Hardware & Infra | Application server refresh | 932.85 | CAD | Posted
2026-03-07 | AP-500019 | V-10078 | Ironwood Contracting Group | INV-8818 | PO-2026-1080 | Contractor Labour | QA analyst - monthly | 17594.78 | CAD | Posted
2026-01-28 | GJ-500103 |  | (Internal journal) |  |  | Internal Labour | Internal labour recharge - monthly | 15355.28 | CAD | Posted
2026-05-21 | AP-500071 | V-10044 | Cascade Cloud Services Inc | INV-8870 | PO-2026-1024 | Cloud / Hosting | Non-prod environment hosting | 3297.81 | CAD | Posted
2026-05-04 | AP-500080 | V-10133 | Keystone Training Partners | INV-8879 | PO-2026-1031 | Training & Change | End-user training materials | 245.73 | CAD | Posted
2026-05-26 | AP-500095 | V-10150 | Harbourview Travel Management | INV-8894 | PO-2026-1021 | Travel | Vendor site visit | 855.13 | CAD | Posted
2026-08-17 | AP-500086 | V-10133 | Keystone Training Partners | INV-8885 | PO-2026-1033 | Training & Change | Super-user training cohort | 740.51 | CAD | Posted
2026-07-04 | AP-500043 | V-10102 | Northgate Software Licensing | INV-8842 | PO-2026-1074 | Software Licences | Core platform licence - annual | 2623.37 | CAD | Posted
2026-08-27 | AP-500087 | V-10133 | Keystone Training Partners | INV-8886 | PO-2026-1099 | Training & Change | Change readiness workshops | 725.79 | CAD | Posted
2026-06-22 | AP-500073 | V-10044 | Cascade Cloud Services Inc | INV-8872 | PO-2026-1040 | Cloud / Hosting | Compute - monthly usage | 3567.04 | CAD | Posted
2026-08-24 | AP-500061 | V-10119 | Summit Hardware Solutions | INV-8860 | PO-2026-1013 | Hardware & Infra | Load balancer appliance | 472.31 | CAD | Posted
2026-01-16 | AP-500063 | V-10044 | Cascade Cloud Services Inc | INV-8862 | PO-2026-1003 | Cloud / Hosting | Storage - monthly | 1384.29 | CAD | Posted
2026-02-14 | AP-500036 | V-10102 | Northgate Software Licensing | INV-8835 | PO-2026-1054 | Software Licences | Test automation licence | 2266.46 | CAD | Posted
2026-04-03 | AP-500068 | V-10044 | Cascade Cloud Services Inc | INV-8867 | PO-2026-1014 | Cloud / Hosting | Non-prod environment hosting | 2694.93 | CAD | Posted
2026-06-22 | AP-500024 | V-10078 | Ironwood Contracting Group | INV-8823 | PO-2026-1041 | Contractor Labour | Solution architect - part time | 11242.88 | CAD | Posted
2026-07-26 | AP-500100 | V-10150 | Harbourview Travel Management | INV-8899 | PO-2026-1069 | Travel | Onsite integration workshop | 396.99 | CAD | Posted
2026-04-24 | AP-500021 | V-10078 | Ironwood Contracting Group | INV-8820 | PO-2026-1068 | Contractor Labour | Data migration specialist | 13205.76 | CAD | Posted
2026-08-04 | AP-500060 | V-10119 | Summit Hardware Solutions | INV-8859 | PO-2026-1045 | Hardware & Infra | Network switch upgrade | 496.17 | CAD | Posted
2026-02-10 | AP-500048 | V-10119 | Summit Hardware Solutions | INV-8847 | PO-2026-1033 | Hardware & Infra | Storage expansion | 13861.41 | CAD | Posted
2026-06-03 | AP-500057 | V-10119 | Summit Hardware Solutions | INV-8856 | PO-2026-1042 | Hardware & Infra | Network switch upgrade | 1604.7 | CAD | Posted
2026-06-05 | AP-500096 | V-10150 | Harbourview Travel Management | INV-8895 | PO-2026-1082 | Travel | Vendor site visit | 290.86 | CAD | Posted
2026-02-11 | AP-500064 | V-10044 | Cascade Cloud Services Inc | INV-8863 | PO-2026-1020 | Cloud / Hosting | Compute - monthly usage | 1441.04 | CAD | Posted
2026-05-09 | AP-500055 | V-10119 | Summit Hardware Solutions | INV-8854 | PO-2026-1087 | Hardware & Infra | Load balancer appliance | 2474.88 | CAD | Posted
2026-02-10 | AP-500003 | V-10021 | Meridian Systems Integration Ltd | INV-8802 | PO-2026-1064 | SI Partner Fees | Cutover support | 7856.94 | CAD | Posted
2026-07-04 | AP-500045 | V-10102 | Northgate Software Licensing | INV-8844 | PO-2026-1065 | Software Licences | Core platform licence - annual | 2158.22 | CAD | Posted
2026-03-10 | AP-500066 | V-10044 | Cascade Cloud Services Inc | INV-8865 | PO-2026-1003 | Cloud / Hosting | Storage - monthly | 1682.01 | CAD | Posted
2026-06-24 | AP-500010 | V-10021 | Meridian Systems Integration Ltd | INV-8809 | PO-2026-1029 | SI Partner Fees | Integration build - phase billing | 29765.11 | CAD | Posted
2026-03-03 | AP-500049 | V-10119 | Summit Hardware Solutions | INV-8848 | PO-2026-1058 | Hardware & Infra | Application server refresh | 8344.83 | CAD | Posted
2026-06-23 | AP-500056 | V-10119 | Summit Hardware Solutions | INV-8855 | PO-2026-1054 | Hardware & Infra | Load balancer appliance | 1638.1 | CAD | Posted
2026-05-22 | AP-500070 | V-10044 | Cascade Cloud Services Inc | INV-8869 | PO-2026-1065 | Cloud / Hosting | Compute - monthly usage | 2776.18 | CAD | Posted
2026-08-15 | AP-500046 | V-10102 | Northgate Software Licensing | INV-8845 | PO-2026-1015 | Software Licences | API gateway licence | 7734.13 | CAD | Posted
2026-04-06 | AP-500007 | V-10021 | Meridian Systems Integration Ltd | INV-8806 | PO-2026-1011 | SI Partner Fees | UAT support services | 46178.32 | CAD | Posted
2026-07-15 | AP-500074 | V-10044 | Cascade Cloud Services Inc | INV-8873 | PO-2026-1089 | Cloud / Hosting | Non-prod environment hosting | 3250.35 | CAD | Posted
2026-02-26 | AP-500017 | V-10166 | Vantage Consulting Associates | INV-8816 | PO-2026-1074 | Contractor Labour | Solution architect - part time | 4321.93 | CAD | Posted
2026-04-24 | AP-500078 | V-10133 | Keystone Training Partners | INV-8877 | PO-2026-1010 | Training & Change | End-user training materials | 139.2 | CAD | Posted
2026-02-10 | AP-500089 | V-10150 | Harbourview Travel Management | INV-8888 | PO-2026-1049 | Travel | Steering committee travel | 605.26 | CAD | Posted
2026-04-04 | AP-500040 | V-10102 | Northgate Software Licensing | INV-8839 | PO-2026-1083 | Software Licences | Core platform licence - annual | 7278.72 | CAD | Posted
2026-03-16 | AP-500091 | V-10150 | Harbourview Travel Management | INV-8890 | PO-2026-1049 | Travel | Steering committee travel | 546.27 | CAD | Posted
2026-06-17 | AP-500111 | V-10150 | Harbourview Travel Management | INV-8896 | PO-2026-1023 | Travel | Onsite integration workshop | 333.65 | CAD | Posted
2026-01-05 | AP-500033 | V-10102 | Northgate Software Licensing | INV-8832 | PO-2026-1065 | Software Licences | API gateway licence | 13811.6 | CAD | Posted
2026-06-27 | AP-500082 | V-10133 | Keystone Training Partners | INV-8881 | PO-2026-1098 | Training & Change | Super-user training cohort | 586.07 | CAD | Posted
2026-02-25 | AP-500090 | V-10150 | Harbourview Travel Management | INV-8889 | PO-2026-1027 | Travel | Onsite integration workshop | 435.29 | CAD | Posted
2026-04-19 | AP-500077 | V-10133 | Keystone Training Partners | INV-8876 | PO-2026-1060 | Training & Change | Change readiness workshops | 140.5 | CAD | Posted
2026-06-10 | AP-500011 | V-10021 | Meridian Systems Integration Ltd | INV-8810 | PO-2026-1012 | SI Partner Fees | UAT support services | 31234.33 | CAD | Posted
2026-07-07 | AP-500027 | V-10078 | Ironwood Contracting Group | INV-8826 | PO-2026-1084 | Contractor Labour | Solution architect - part time | 13951.7 | CAD | Posted
2026-04-20 | AP-500093 | V-10150 | Harbourview Travel Management | INV-8892 | PO-2026-1095 | Travel | Steering committee travel | 422.02 | CAD | Posted
2026-04-22 | AP-500052 | V-10119 | Summit Hardware Solutions | INV-8851 | PO-2026-1083 | Hardware & Infra | Application server refresh | 6097.24 | CAD | Posted
2026-03-20 | AP-500050 | V-10119 | Summit Hardware Solutions | INV-8849 | PO-2026-1027 | Hardware & Infra | Load balancer appliance | 9947.06 | CAD | Posted
2026-01-25 | AP-500088 | V-10150 | Harbourview Travel Management | INV-8887 | PO-2026-1036 | Travel | Onsite integration workshop | 1077.34 | CAD | Posted
2026-07-09 | AP-500075 | V-10044 | Cascade Cloud Services Inc | INV-8874 | PO-2026-1053 | Cloud / Hosting | Data egress charges | 3457.49 | CAD | Posted
2026-06-18 | AP-500112 | V-10021 | Meridian Systems Integration Ltd | CN-8902 | PO-2026-1012 | SI Partner Fees | Credit note - overbilled sprint 4 | -18450 | CAD | Posted
2026-02-10 | AP-500005 | V-10021 | Meridian Systems Integration Ltd | INV-8804 | PO-2026-1057 | SI Partner Fees | Cutover support | 7641.81 | CAD | Posted
2026-08-15 | AP-500076 | V-10044 | Cascade Cloud Services Inc | INV-8875 | PO-2026-1070 | Cloud / Hosting | Compute - monthly usage | 6663.84 | CAD | Posted
2026-08-04 | AP-500015 | V-10021 | Meridian Systems Integration Ltd | INV-8814 | PO-2026-1040 | SI Partner Fees | UAT support services | 28059.14 | CAD | Posted
2026-05-18 | AP-500041 | V-10102 | Northgate Software Licensing | INV-8840 | PO-2026-1027 | Software Licences | Test automation licence | 7871.98 | CAD | Posted
2026-05-03 | AP-500022 | V-10166 | Vantage Consulting Associates | INV-8821 | PO-2026-1092 | Contractor Labour | Data migration specialist | 14892.81 | CAD | Posted
2026-04-28 | GJ-500106 |  | (Internal journal) |  |  | Internal Labour | Internal labour recharge - monthly | 24028.65 | CAD | Posted
2026-08-27 | AP-500101 | V-10150 | Harbourview Travel Management | INV-8900 | PO-2026-1003 | Travel | Onsite integration workshop | 483.46 | CAD | Posted

## Committed POs
Committed Costs — open purchase orders
POs raised, goods/services not yet invoiced. THIS is what juniors forget.
PO Number | Vendor ID | Vendor Name | Cost Category | Description | Committed Amount | Expected Delivery | Status
PO-2026-1088 | V-10021 | Meridian Systems Integration Ltd | SI Partner Fees | Sprint 9-10 delivery | 78000 | 2026-09-30 | Open
PO-2026-1091 | V-10078 | Ironwood Contracting Group | Contractor Labour | Sep-Nov contractor extension | 64500 | 2026-11-30 | Open
PO-2026-1094 | V-10102 | Northgate Software Licensing | Software Licences | Production licence uplift | 32000 | 2026-10-15 | Open
PO-2026-1096 | V-10133 | Keystone Training Partners | Training & Change | End-user training delivery | 18500 | 2026-10-31 | Open
PO-2026-1099 | V-10044 | Cascade Cloud Services Inc | Cloud / Hosting | Prod environment - Sep to Dec | 21600 | 2026-12-31 | Open
|  |  |  | TOTAL COMMITTED | 214600

## Cost Dashboard
Cost Control Dashboard — Budget · Actual · Committed · EAC
Period ending 31 Aug 2026 (Month 8 of 12). FX: USD invoices converted @1.36.
Cost Category | Budget (BAC) | YTD Budget | Actual (posted) | Committed (PO) | Est. to Complete | Forecast (EAC) | Variance at Completion | Var %
SI Partner Fees | 420000 | 306600 | 323968.73 | 78000 | 35400 | 437368.73 | -17368.73 | -4.135%
Internal Labour | 260000 | 171600 | 171047.1 | 0 | 88400 | 259447.1 | 552.9 | 0.2127%
Contractor Labour | 180000 | 144000 | 179550.05 | 64500 | 0 | 244050.05 | -64050.05 | -35.58%
Software Licences | 145000 | 94250 | 112919.36 | 32000 | 18750 | 163669.36 | -18669.36 | -12.88%
Hardware & Infra | 90000 | 85500 | 60880.94 | 0 | 4500 | 65380.94 | 24619.06 | 27.35%
Cloud / Hosting | 60000 | 36000 | 38800.06 | 21600 | 2400 | 62800.06 | -2800.06 | -4.667%
Training & Change | 25000 | 10000 | 5578.96 | 18500 | 0 | 24078.96 | 921.04 | 3.684%
Travel | 12000 | 8400 | 7945.62 | 0 | 3600 | 11545.62 | 454.38 | 3.787%
Contingency | 68000 | 44880 | 0 | 0 | 23120 | 23120 | 44880 | 66%
TOTAL | 1260000 | 901230 | 900690.82 | 214600 | 176170 | 1291460.82 | -31460.82 | -2.497%
HEADLINE
Budget at Completion (BAC) |  |  | 1260000
Actual to date (posted) |  |  | 900690.82
% of budget spent |  |  | 71.48%
YTD variance (Actual vs YTD Budget) |  |  | 539.18
Committed (open POs) |  |  | 214600
Unposted invoices (pending) |  |  | 28220
Forecast at Completion (EAC) |  |  | 1291460.82
VARIANCE AT COMPLETION |  |  | -31460.82
Contingency remaining |  |  | 44880
COST RAG |  |  | AMBER
S-Curve data (cumulative)
Month | Cumulative Plan | Cumulative Actual
Jan | 85600 | 0
Feb | 164250 | 0
Mar | 277540 | 0
Apr | 401490 | 0
May | 531750 | 0
Jun | 658260 | 0
Jul | 783470 | 0
Aug | 901230 | 0
Sep | 1013690
Oct | 1121100
Nov | 1197050
Dec | 1260000

## RAID Log
RAID Log
Risks · Assumptions · Issues · Dependencies. Reviewed weekly; High items escalated to steering.
ID | Type | Description | Owner | Impact | Mitigation / Response | Status | Raised
I-001 | Issue | Contractor Labour is tracking 22% over plan ($179.5K actual vs $144K YTD budget). Forecast to land $64K over at completion. | IT Delivery Lead | High | Root cause: two extra contractors onboarded in Mar to recover the integration build. CR-003 raised to draw down contingency. Rate card renegotiation underway. | Open | 2026-06-12
I-002 | Issue | Duplicate invoice detected in the D365 AP export — same invoice number posted against two vouchers. | Finance Business Partner | Medium | Flagged to AP; credit/reversal requested. Excluded from the EAC pending correction. Root cause: manual re-key after a failed batch. | Open | 2026-08-14
I-003 | Issue | One hardware invoice posted with NO PO reference — breaches procurement policy (no-PO-no-pay). | Procurement | Medium | Retrospective PO raised; exception logged. Control added: monthly PO-compliance check on the AP export. | Open | 2026-07-22
I-004 | Issue | Two vendor invoices ($28.2K) remain unposted/pending approval at month-end — understating reported actuals. | Finance Business Partner | Medium | Tracked separately on the dashboard; will be accrued into the August position so the month is not understated. | Open | 2026-08-29
R-001 | Risk | SI partner (Meridian) has slipped delivery on two prior engagements. Sprint 9-10 ($78K PO) is on the critical path to UAT. | SI Engagement Mgr | High | Milestone-based billing with 10% holdback; weekly delivery call; recovery plan required if any sprint slips >3 days. | Open | 2026-02-10
R-002 | Risk | UAT window (Oct) overlaps with the retail quarter-end close — business testers may be unavailable. | Business Owner | High | Testers pre-booked; backup super-users identified; CR-004 requests a 2-week UAT extension. | Mitigated | 2026-05-18
R-003 | Risk | USD-denominated licence invoices expose the project to FX movement (currently ~$14.9K USD posted). | Finance Business Partner | Low | FX rate fixed at 1.36 for forecasting; exposure is immaterial (<2% of budget). Monitor quarterly. | Open | 2026-05-14
R-004 | Risk | Contingency ($68K) may be exhausted by the contractor overrun, leaving no buffer for cutover issues. | PCO | High | Contingency drawdown tracked; $44.9K remains. No further drawdown without sponsor approval (per CR governance). | Open | 2026-08-01
A-001 | Assumption | Business testers are available for the full UAT window outside quarter-end. | Business Owner | Medium | Confirmed at kickoff; being re-tested — see R-002. If it fails, the go-live date moves. | Open | 2026-01-15
A-002 | Assumption | No further regulatory (OSFI B-13) requirements land before go-live. | Risk & Compliance | Medium | Confirmed with Risk & Compliance at the design gate. Re-verified quarterly. | Open | 2026-01-15
D-001 | Dependency | GL opening-balance load depends on Finance closing the FY25 books. | Finance Business Partner | High | Confirmed complete 2026-03-20. Load proceeded on schedule. | Closed | 2026-01-20
D-002 | Dependency | Production cutover depends on the Infrastructure team completing the network upgrade. | IT Delivery Lead | High | Scheduled for Oct; tracked on the schedule as a hard predecessor to cutover. | Open | 2026-04-02

## Change Control Log
Change Control Log
Every change to baselined scope, cost or schedule. Sponsor approves >$25K.
CR ID | Change requested | Raised by | Cost impact | Sched. | Priority | Status | Approver | Decided | Rationale / decision note
CR-001 | Add real-time payment notifications to scope | Business Owner | +$46,000 | +10d | Medium | Approved | VP Digital Banking | 2026-03-06 | Competitive necessity. Funded from contingency; sponsor approved at March steering.
CR-002 | Defer wealth-module integration to Phase 2 | IT Delivery Lead | -$38,000 | -15d | Medium | Approved | VP Digital Banking | 2026-04-17 | De-scoped to protect the go-live date. Credit returned to contingency.
CR-003 | Draw down $64K contingency to cover contractor overrun | PCO | $0 (net) | 0 | High | Approved | VP Digital Banking | 2026-08-20 | Contingency exists for exactly this. Rate renegotiation to prevent recurrence. Links to I-001.
CR-004 | Extend UAT window by 2 weeks (quarter-end clash) | Business Owner | +$12,000 | +10d | High | Under Review | VP Digital Banking | — | Protects test quality over the date. Links to R-002. Decision due at Sept steering.
CR-005 | Upgrade to premium support tier for hypercare | SI Engagement Mgr | +$28,000 | 0 | Low | REJECTED | VP Digital Banking | 2026-07-30 | Standard support is contractually sufficient for a 2-week hypercare. Not justified.
CR-006 | Add OSFI B-13 evidence pack to deliverables | Risk & Compliance | +$8,500 | +3d | High | Approved | VP Digital Banking | 2026-02-25 | Regulatory — non-negotiable. Absorbed within contingency.

## Action Register
Action Item Register
Every action traces to a RAID or CR ID.
ID | Action | Ref (RAID/CR) | Owner | Raised | Due | Status | Notes
AI-001 | Renegotiate contractor rate card with Ironwood | I-001 | IT Delivery Lead | 2026-06-12 | 2026-09-15 | In Progress | Draft terms received; 8% reduction offered.
AI-002 | Obtain credit note for the duplicate invoice | I-002 | Finance Business Partner | 2026-08-14 | 2026-09-10 | In Progress | Vendor acknowledged; credit expected in Sept.
AI-003 | Raise retrospective PO for the no-PO hardware invoice | I-003 | Procurement | 2026-07-22 | 2026-08-05 | Closed | PO-2026-1087 raised; exception logged.
AI-004 | Add monthly PO-compliance check to the cost process | I-003 | PCO | 2026-07-22 | 2026-08-31 | Closed | Control added to the month-end checklist.
AI-005 | Accrue the two pending invoices into the August position | I-004 | PCO | 2026-08-29 | 2026-09-05 | Open | $28.2K to be accrued so August is not understated.
AI-006 | Confirm UAT tester availability against quarter-end | R-002/A-001 | Business Owner | 2026-05-18 | 2026-09-12 | Open | Drives the CR-004 decision at Sept steering.
AI-007 | Prepare contingency drawdown paper for sponsor | I-001/CR-003 | PCO | 2026-08-01 | 2026-08-18 | Closed | Approved at August steering.
AI-008 | Confirm network upgrade completion date with Infrastructure | D-002 | IT Delivery Lead | 2026-04-02 | 2026-09-30 | Open | Hard predecessor to cutover.

## Decision Log
Decision Log
What was decided, by whom, and WHY — so nobody re-litigates it in month nine.
ID | Date | Decision | Decided by | Rationale
DEC-01 | 2026-03-06 | Add real-time payment notifications (CR-001), funded from contingency. | VP Digital Banking | Competitors launched the feature; going live without it would require an immediate follow-up release. Cheaper to absorb now.
DEC-02 | 2026-04-17 | Defer the wealth module to Phase 2 (CR-002). | VP Digital Banking | Protects the go-live date. The module serves 4% of customers; the delay is acceptable to the business.
DEC-03 | 2026-08-20 | Draw down $64K contingency to cover the contractor overrun (CR-003). | VP Digital Banking | Contingency exists for exactly this. The alternative — cutting scope late — carries more risk than the cost.
DEC-04 | 2026-07-30 | Reject the premium support upgrade (CR-005). | VP Digital Banking | Standard support is contractually sufficient for a 2-week hypercare. Not justified on evidence.
DEC-05 | 2026-08-29 | Report the project AMBER on cost despite a near-zero YTD variance. | PCO / Sponsor | YTD actuals look on-plan, but adding $214.6K of committed POs forecasts a $31K overrun. Reporting Green on YTD alone would have been misleading.

## Milestone Tracker
Milestone Tracker
Baseline vs Forecast vs Actual. Slippage in working days. Source: MS Project schedule.
ID | Milestone | Baseline | Forecast | Actual | Slip (days) | Status
M1 | Project approved & funded | 2026-01-15 | 2026-01-15 | 2026-01-15 | 0 | Met
M2 | Design baselined | 2026-03-12 | 2026-03-12 | 2026-03-18 | 4 | Met (late)
M3 | Build complete | 2026-07-09 | 2026-07-09 | 2026-07-16 | 5 | Met (late)
M4 | UAT signed off | 2026-10-15 | 2026-10-29 | — | 10 | At Risk
M5 | GO-LIVE | 2026-11-05 | 2026-11-19 | — | 10 | At Risk
M6 | Project closed | 2026-11-26 | 2026-12-10 | — | 10 | At Risk
Note: the 10-day slip on M4-M6 is driven by CR-004 (UAT extension, under review). If CR-004 is approved, these become the new baseline.

## Status Report
Status Report — Period ending 31 Aug 2026
Northbridge Digital Banking Platform Upgrade · PRJ-2026-0147 · Month 8 of 12 · For September Steering Committee
Overall | AMBER
Schedule | AMBER
Cost | AMBER
Scope | GREEN
Quality | GREEN
Cost Amber: YTD spend is on plan, but $214.6K of committed POs forecasts a $31.5K overrun at completion. Contingency covers it — see CR-003.
Schedule Amber: 10-day forecast slip to go-live, driven by the UAT window clash with quarter-end (R-002 / CR-004, under review).
Cost position
• Budget (BAC) $1,260,000 · Actual to date $900,691 (71.5% spent) · Committed $214,600 · Forecast (EAC) $1,291,461.
• YTD variance is effectively nil (-0.1%) — but that is not the story. Adding committed POs, the project forecasts $31,461 OVER budget (-2.5%).
• Driver: Contractor Labour, 22% over plan (I-001) — two extra contractors onboarded in March to recover the integration build.
• Contingency of $44,880 remains after the CR-003 drawdown — sufficient to absorb the overrun. No additional funding requested.
Accomplished this period
• Build complete (M3) — 5 days late, absorbed without impacting UAT start.
• Vendor master, open AP and GL opening balances migrated and reconciled.
• CR-003 (contingency drawdown) approved at August steering; contractor rate renegotiation underway (AI-001).
Planned next period
• UAT preparation and test-case sign-off; decision on CR-004 (UAT extension) at September steering.
• Close the duplicate-invoice credit (I-002) and accrue the two pending invoices (I-004).
• Confirm the network upgrade date with Infrastructure (D-002) — hard predecessor to cutover.
Decisions required from Steering
• APPROVE CR-004: extend UAT by 2 weeks to avoid the quarter-end clash. Cost +$12K, go-live moves 10 working days.
• RECOMMENDATION: approve. Compressing UAT to hold the date would trade a 2-week delay for a live defect in a payment system.
Top risks & issues
• I-001 (High, Open): Contractor Labour 22% over — mitigated by CR-003; rate renegotiation in progress.
• R-001 (High, Open): SI partner delivery record — sprint 9-10 on the critical path to UAT.
• R-004 (High, Open): Contingency buffer depleting; $44.9K remains for cutover contingency.
• R-002 (High, Mitigated): UAT / quarter-end clash — CR-004 raised.