## Portfolio Dashboard
Portfolio Dashboard
Meridian Digital Consulting · 6 active projects · period ending 31 Aug 2026 (month 8 of 12). Every figure computes from the data tabs — change an input and this refreshes.
PORTFOLIO HEADLINE
Portfolio revenue | 2215000
Cost budget | 1640000
Actual cost to date | 1448625.86
Committed cost | 177000
Forecast cost (EAC) | 1868477.3
Planned margin | 25.96%
Forecast margin | 15.64%
Margin erosion | 10.32%
BY PROJECT — computed status vs what the PM reported
Project | PM | Revenue | Cost Budget | YTD Budget | Actual | Committed | Forecast (EAC) | Variance | Var % | Margin % | COMPUTED RAG | PM SAID | FLAG
Retail Bank Mobile App Rollout | G. Liu | 485000 | 352000 | 352000.02 | 357727.2 | 18500 | 376227.2 | -24227.2 | -6.883% | 22.43% | AMBER | Green | UNDER-REPORTED
Wealth Platform Data Migration | G. Liu | 312000 | 236000 | 219268.19 | 206114.26 | 9200 | 232046.09 | 3953.91 | 1.675% | 25.63% | GREEN | Amber | mismatch
Insurance Claims Automation | O. Haddad | 640000 | 470000 | 371078.71 | 381081.15 | 86500 | 566502.43 | -96502.43 | -20.53% | 11.48% | RED | Green | UNDER-REPORTED
Core Banking API Layer | O. Haddad | 228000 | 171000 | 139269.43 | 151410.48 | 21000 | 204141.07 | -33141.07 | -19.38% | 10.46% | RED | Green | UNDER-REPORTED
Regulatory Reporting Dashboard | G. Liu | 156000 | 112000 | 112000 | 112702.04 | 0 | 112702.04 | -702.04 | -0.6268% | 27.76% | GREEN | Green
Payments Fraud Model Uplift | O. Haddad | 394000 | 299000 | 203532.25 | 239590.73 | 41800 | 376858.47 | -77858.47 | -26.04% | 4.351% | RED | Amber | mismatch
PORTFOLIO |  | 2215000 | 1640000 | 1397148.6 | 1448625.86 | 177000 | 1868477.3 | -228477.3 | -13.93% | 15.64%
DELIVERY HEALTH
Milestones at risk |  |  |  | 7
Milestones met late |  |  |  | 7
Worst milestone slip (days) |  |  |  | 42
Benefits Red or Dropped |  |  |  | 1
Projects PM-reported Green but computed worse |  |  |  | 3

## Projects
Project Portfolio — master
6 client projects · revenue, cost budget, PM. All dashboard figures compute from this data.
Project ID | Project Name | Billing Type | Contract Value (Revenue) | Cost Budget | Start | End | Project Manager
PRJ-OP-201 | Retail Bank Mobile App Rollout | Fixed Price | 485000 | 352000 | 2026-01-12 | 2026-08-28 | G. Liu
PRJ-OP-202 | Wealth Platform Data Migration | Time & Material | 312000 | 236000 | 2026-02-02 | 2026-09-30 | G. Liu
PRJ-OP-203 | Insurance Claims Automation | Fixed Price | 640000 | 470000 | 2026-01-05 | 2026-11-20 | O. Haddad
PRJ-OP-204 | Core Banking API Layer | Time & Material | 228000 | 171000 | 2026-03-16 | 2026-10-15 | O. Haddad
PRJ-OP-205 | Regulatory Reporting Dashboard | Fixed Price | 156000 | 112000 | 2026-04-01 | 2026-08-14 | G. Liu
PRJ-OP-206 | Payments Fraud Model Uplift | Time & Material | 394000 | 299000 | 2026-02-23 | 2026-12-04 | O. Haddad

## Budget
Cost Budget — by project by month
Baselined plan. Total column drives the dashboard.
Project ID | Project Name | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total Cost Budget
PRJ-OP-201 | Retail Bank Mobile App Rollout | 24955.95 | 40360.81 | 52151.17 | 58532.08 | 58532.08 | 52151.17 | 40360.81 | 24955.95 | 0 | 0 | 0 | 0 | 352000.02
PRJ-OP-202 | Wealth Platform Data Migration | 0 | 16731.83 | 27060.09 | 34964.99 | 39243.1 | 39243.1 | 34964.99 | 27060.09 | 16731.83 | 0 | 0 | 0 | 236000.02
PRJ-OP-203 | Insurance Claims Automation | 22085.61 | 33440.17 | 43395.5 | 51145.07 | 56061.05 | 57745.19 | 56061.05 | 51145.07 | 43395.5 | 33440.17 | 22085.61 | 0 | 469999.99
PRJ-OP-204 | Core Banking API Layer | 0 | 0 | 12123.49 | 19607.1 | 25334.8 | 28434.62 | 28434.62 | 25334.8 | 19607.1 | 12123.49 | 0 | 0 | 171000.02
PRJ-OP-205 | Regulatory Reporting Dashboard | 0 | 0 | 0 | 15088.36 | 25898.11 | 30027.06 | 25898.11 | 15088.36 | 0 | 0 | 0 | 0 | 112000
PRJ-OP-206 | Payments Fraud Model Uplift | 0 | 14050.21 | 21273.64 | 27606.92 | 32536.97 | 35664.37 | 36735.77 | 35664.37 | 32536.97 | 27606.92 | 21273.64 | 14050.21 | 298999.99

## Actuals
Actual Cost — by project by month
Posted actuals through August (month 8 of 12). Sep–Dec are zero — not yet incurred.
Project ID | Project Name | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total Actual
PRJ-OP-201 | Retail Bank Mobile App Rollout | 26216.47 | 40451.32 | 51813.77 | 61628.47 | 57404.54 | 53067.79 | 41406.37 | 25738.47 | 0 | 0 | 0 | 0 | 357727.2
PRJ-OP-202 | Wealth Platform Data Migration | 0 | 15170.32 | 25768.81 | 32869.13 | 38183.74 | 35148.67 | 34369.69 | 24603.9 | 0 | 0 | 0 | 0 | 206114.26
PRJ-OP-203 | Insurance Claims Automation | 23461 | 34468.57 | 46197.83 | 51008.82 | 56712.07 | 57022.21 | 59352.29 | 52858.36 | 0 | 0 | 0 | 0 | 381081.15
PRJ-OP-204 | Core Banking API Layer | 0 | 0 | 13060.06 | 21092.87 | 26943.19 | 30615.97 | 31752.13 | 27946.26 | 0 | 0 | 0 | 0 | 151410.48
PRJ-OP-205 | Regulatory Reporting Dashboard | 0 | 0 | 0 | 15242.59 | 24552.8 | 30735.97 | 26875.15 | 15295.53 | 0 | 0 | 0 | 0 | 112702.04
PRJ-OP-206 | Payments Fraud Model Uplift | 0 | 16982.35 | 25980.85 | 31256.58 | 38244.8 | 40313.62 | 44568.76 | 42243.77 | 0 | 0 | 0 | 0 | 239590.73

## Committed
Committed Cost — raised, not yet in actuals
Contracted extensions and open POs. THIS is what turns a Green project Red.
Project ID | Project Name | Committed Cost | Description
PRJ-OP-201 | Retail Bank Mobile App Rollout | 18500 | Hypercare support extension
PRJ-OP-202 | Wealth Platform Data Migration | 9200 | Contract data engineer Sep-Oct
PRJ-OP-203 | Insurance Claims Automation | 86500 | 2 contractors extended to Nov + licence uplift
PRJ-OP-204 | Core Banking API Layer | 21000 | API gateway licences
PRJ-OP-205 | Regulatory Reporting Dashboard | 0 | None
PRJ-OP-206 | Payments Fraud Model Uplift | 41800 | ML specialist extension to Dec
| TOTAL | 177000

## Milestones
Milestone Tracker — all projects
Baseline vs forecast vs actual. Slippage is computed, not typed.
Project ID | Milestone ID | Milestone | Baseline Date | Forecast Date | Actual Date | Status | Slip (days)
PRJ-OP-201 | M1 | Design sign-off | 2026-02-20 | 2026-02-20 | 2026-02-20 | Met | 0
PRJ-OP-201 | M2 | Build complete | 2026-05-29 | 2026-06-05 | 2026-06-05 | Met (late) | 7
PRJ-OP-201 | M3 | UAT sign-off | 2026-07-24 | 2026-07-31 | 2026-07-31 | Met (late) | 7
PRJ-OP-201 | M4 | Go-live | 2026-08-28 | 2026-08-28 |  | On Track | 0
PRJ-OP-202 | M1 | Data mapping approved | 2026-03-13 | 2026-03-27 | 2026-03-27 | Met (late) | 14
PRJ-OP-202 | M2 | Trial migration | 2026-06-12 | 2026-07-10 | 2026-07-10 | Met (late) | 28
PRJ-OP-202 | M3 | Cutover | 2026-09-30 | 2026-10-16 |  | At Risk | 16
PRJ-OP-203 | M1 | Requirements baselined | 2026-02-13 | 2026-02-13 | 2026-02-13 | Met | 0
PRJ-OP-203 | M2 | Model build complete | 2026-06-30 | 2026-07-24 | 2026-07-24 | Met (late) | 24
PRJ-OP-203 | M3 | UAT sign-off | 2026-09-25 | 2026-10-23 |  | At Risk | 28
PRJ-OP-203 | M4 | Go-live | 2026-11-20 | 2026-12-18 |  | At Risk | 28
PRJ-OP-204 | M1 | API spec approved | 2026-04-17 | 2026-04-17 | 2026-04-17 | Met | 0
PRJ-OP-204 | M2 | Integration complete | 2026-08-14 | 2026-08-28 |  | At Risk | 14
PRJ-OP-204 | M3 | Go-live | 2026-10-15 | 2026-10-30 |  | At Risk | 15
PRJ-OP-205 | M1 | Report specs signed | 2026-05-01 | 2026-05-01 | 2026-05-01 | Met | 0
PRJ-OP-205 | M2 | Go-live | 2026-08-14 | 2026-08-14 | 2026-08-14 | Met | 0
PRJ-OP-206 | M1 | Model design approved | 2026-04-10 | 2026-04-24 | 2026-04-24 | Met (late) | 14
PRJ-OP-206 | M2 | Training data ready | 2026-07-03 | 2026-08-07 | 2026-08-07 | Met (late) | 35
PRJ-OP-206 | M3 | Model validation | 2026-10-09 | 2026-11-13 |  | At Risk | 35
PRJ-OP-206 | M4 | Production deploy | 2026-12-04 | 2027-01-15 |  | At Risk | 42
Formulas:
Slip (days) = IF(OR([Baseline Date]="",[Forecast Date]=""),"",DATEDIF(DATEVALUE([Baseline Date]),DATEVALUE([Forecast Date]),"d"))

## Benefits
Benefits Register
What each project promised vs what it is delivering. One benefit was quietly dropped — find it.
Project ID | Benefit ID | Benefit | Target | Current | RAG | Note
PRJ-OP-201 | BEN-01 | Digital channel adoption +15% | 15% uplift | 12% (tracking) | Amber | Partial - adoption slower in 45+ segment
PRJ-OP-202 | BEN-02 | Legacy platform decommission saving $180K/yr | $180K/yr | $180K/yr | Green | On track - decommission scheduled post-cutover
PRJ-OP-203 | BEN-03 | Claims handling time -30% | 30% reduction | 22% (tracking) | Amber | Automation scope reduced under CR-02
PRJ-OP-204 | BEN-04 | Partner integration time 6wks -> 2wks | 4 wks saved | 4 wks saved | Green | Validated with 2 pilot partners
PRJ-OP-205 | BEN-05 | Regulatory reporting effort -40% | 40% reduction | 41% | Green | Delivered and measured post go-live
PRJ-OP-206 | BEN-06 | Fraud detection recall +8pts | +8 pts | Not yet measurable | Grey | Measurable only after production deploy
PRJ-OP-201 | BEN-07 | Branch call volume -10% | 10% reduction | DROPPED | Red | Quietly de-scoped in month 4; never formally closed or re-baselined

## PM Reported RAG
What the PMs self-report
Compare against the computed RAG on the Portfolio Dashboard. Where they disagree is the PCO's job.
Project ID | PM Reported Overall | PM Reported Cost | PM Reported Schedule | PM Commentary
PRJ-OP-201 | Green | Green | Amber | On track for Aug go-live
PRJ-OP-202 | Amber | Amber | Amber | Cutover date under pressure
PRJ-OP-203 | Green | Green | Green | Reported on budget and on plan
PRJ-OP-204 | Amber | Green | Amber | Integration slipping 2 weeks
PRJ-OP-205 | Green | Green | Green | Delivered
PRJ-OP-206 | Amber | Amber | Red | Model validation at risk

## Resources
Resource Master — the bench
15 specialists · role, contracted capacity, cost & bill rates.
Resource ID | Resource Name | Role | Resourcing Unit | Capacity (hrs/wk) | Cost Rate | Bill Rate
R-3001 | Amara Okafor | Solution Architect | Architecture | 40 | 95 | 210
R-3002 | Ben Carrow | Senior Developer | Engineering | 40 | 78 | 175
R-3003 | Priya Nair | Senior Developer | Engineering | 40 | 78 | 175
R-3004 | Daniel Kim | Developer | Engineering | 40 | 60 | 140
R-3005 | Sofia Rossi | Developer | Engineering | 40 | 60 | 140
R-3006 | Marcus Bell | QA Lead | Quality | 40 | 68 | 150
R-3007 | Lena Fischer | QA Analyst | Quality | 40 | 52 | 120
R-3008 | Tomas Vega | Data Migration Specialist | Data | 40 | 82 | 185
R-3009 | Hannah Wright | Business Analyst | Advisory | 40 | 70 | 160
R-3010 | Ravi Menon | Business Analyst | Advisory | 32 | 70 | 160
R-3011 | Grace Liu | Project Manager | Delivery | 40 | 88 | 195
R-3012 | Omar Haddad | Scrum Master | Delivery | 40 | 72 | 165
R-3013 | Nina Patel | Data Engineer | Data | 40 | 80 | 180
R-3014 | Jack Thompson | DevOps Engineer | Engineering | 40 | 75 | 170
R-3015 | Yuki Tanaka | UX Designer | Design | 24 | 65 | 150

## Allocations (RAW)
Resource Allocations — raw booking export
351 rows. Contains 7 data defects — see the Defect Log.
Allocation ID | Resource ID | Resource Name | Role | Project ID | Project Name | Week Starting | Booked Hours | Capacity | Booking Status
AL-70271 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 32 | 40 | Confirmed
AL-70137 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-27 | 35 | 40 | Confirmed
AL-70201 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 11 | 40 | Confirmed
AL-70129 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 14 | 40 | Confirmed
AL-70183 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 20 | 40 | Confirmed
AL-70134 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 12 | 40 | Confirmed
AL-70196 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 17 | 40 | Confirmed
AL-70257 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-08 | 12 | 40 | Confirmed
AL-70029 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-204 | Core Banking API Layer | 2026-06-15 | 12 | 40 | Confirmed
AL-70215 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-15 | 14 | 32 | Confirmed
AL-70081 | R-3004 | Daniel Kim | Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 10 | 40 | Confirmed
AL-70236 | R-3011 | Grace Liu | Project Manager | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 17 | 40 | Confirmed
AL-70334 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-203 | Insurance Claims Automation | 2026-07-20 | 8 | 24 | Confirmed
AL-70112 | R-3005 | Sofia Rossi | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 37 | 40 | Confirmed
AL-70009 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 13 | 40 | Confirmed
AL-70068 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-03 | 15 | 40 | Confirmed
AL-70354 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 24 | 32 | Confirmed
AL-70169 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 17 | 40 | Confirmed
AL-70235 | R-3011 | Grace Liu | Project Manager | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-15 | 10 | 40 | Confirmed
AL-70152 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 11 | 40 | Confirmed
AL-70254 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-01 | 20 | 40 | Confirmed
AL-70027 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 7 | 40 | Confirmed
AL-70094 | R-3004 | Daniel Kim | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-08-10 | 12 | 40 | Confirmed
AL-70123 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-08 | 16 | 40 | Confirmed
AL-70239 | R-3011 | Grace Liu | Project Manager | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 17 | 40 | Confirmed
AL-70320 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-08-10 | 16 | 40 | Confirmed
AL-70316 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 19 | 40 | Confirmed
AL-70171 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 16 | 40 | Confirmed
AL-70309 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-29 | 12 | 40 | Confirmed
AL-70219 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 23 | 32 | Confirmed
AL-70252 | R-3011 | Grace Liu | Project Manager | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-10 | 17 | 40 | Confirmed
AL-70207 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-03 | 14 | 40 | Confirmed
AL-70275 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-10 | 19 | 40 | Confirmed
AL-70011 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 14 | 40 | Confirmed
AL-70287 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-29 | 37 | 40 | Confirmed
AL-70186 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 16 | 40 | Confirmed
AL-70333 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-13 | 6 | 24 | Confirmed
AL-70161 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-10 | 10 | 40 | Confirmed
AL-70182 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 13 | 40 | Confirmed
AL-70107 | R-3005 | Sofia Rossi | Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 8 | 40 | Confirmed
AL-70047 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 14 | 40 | Confirmed
AL-70052 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-08 | 17 | 40 | Confirmed
AL-70294 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 17 | 40 | Confirmed
AL-70071 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 17 | 40 | Confirmed
AL-70082 | R-3004 | Daniel Kim | Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 13 | 40 | Confirmed
AL-70286 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 10 | 40 | Confirmed
AL-70349 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-06 | 22 | 40 | Confirmed
AL-70051 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-08 | 16 | 40 | Confirmed
AL-70045 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-10 | 19 | 40 | Confirmed
AL-70086 | R-3004 | Daniel Kim | Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-13 | 17 | 40 | Confirmed
AL-70352 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 24 | 32 | Confirmed
AL-70231 | R-3011 | Grace Liu | Project Manager | PRJ-OP-203 | Insurance Claims Automation | 2026-06-08 | 18 | 40 | Confirmed
AL-70213 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 27 | 32 | Confirmed
AL-70090 | R-3004 | Daniel Kim | Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-20 | 10 | 40 | Confirmed
AL-70023 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-203 | Insurance Claims Automation | 2026-08-17 | 18 | 40 | Confirmed
AL-70091 | R-3004 | Daniel Kim | Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-27 | 38 | 40 | Confirmed
AL-70336 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 10 | 24 | Confirmed
AL-70014 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 31 | 40 | Confirmed
AL-70339 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 18 | 24 | Confirmed
AL-70084 | R-3004 | Daniel Kim | Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-06 | 18 | 40 | Confirmed
AL-70227 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 29 | 32 | Confirmed
AL-70108 | R-3005 | Sofia Rossi | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-06-29 | 16 | 40 | Confirmed
AL-70092 | R-3004 | Daniel Kim | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 29 | 40 | Confirmed
AL-70106 | R-3005 | Sofia Rossi | Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-22 | 10 | 40 | Confirmed
AL-70046 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-10 | 10 | 40 | Confirmed
AL-70064 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-07-20 | 10 | 40 | Confirmed
AL-70025 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-01 | 15 | 40 | Confirmed
AL-70310 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 13 | 40 | Confirmed
AL-70290 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-13 | 15 | 40 | Confirmed
AL-70200 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 17 | 40 | Confirmed
AL-70167 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-01 | 16 | 40 | Confirmed
AL-70317 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 8 | 40 | Confirmed
AL-70289 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 13 | 40 | Confirmed
AL-70020 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 20 | 40 | Confirmed
AL-70216 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 13 | 32 | Confirmed
AL-70016 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 12 | 40 | Confirmed
AL-70279 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 12 | 40 | Confirmed
AL-70176 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 16 | 40 | Confirmed
AL-70280 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-01 | 10 | 40 | Confirmed
AL-70097 | R-3004 | Daniel Kim | Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-17 | 15 | 40 | Confirmed
AL-70179 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 13 | 40 | Confirmed
AL-70173 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-204 | Core Banking API Layer | 2026-06-29 | 22 | 40 | Confirmed
AL-70180 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 9 | 40 | Confirmed
AL-70292 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-07-20 | 15 | 40 | Confirmed
AL-70080 | R-3004 | Daniel Kim | Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 18 | 40 | Confirmed
AL-70295 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-03 | 12 | 40 | Confirmed
AL-70263 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 15 | 40 | Confirmed
AL-70010 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 11 | 40 | Confirmed
AL-70256 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 10 | 40 | Confirmed
AL-70113 | R-3005 | Sofia Rossi | Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-20 | 17 | 40 | Confirmed
AL-70085 | R-3004 | Daniel Kim | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 14 | 40 | Confirmed
AL-70299 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-01 | 19 | 40 | Confirmed
AL-70044 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-03 | 8 | 40 | Confirmed
AL-70139 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-204 | Core Banking API Layer | 2026-08-10 | 20 | 40 | Confirmed
AL-70304 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-06-15 | 13 | 40 | Confirmed
AL-70026 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-08 | 11 | 40 | Confirmed
AL-70281 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 19 | 40 | Confirmed
AL-70135 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-20 | 14 | 40 | Confirmed
AL-70298 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 32 | 40 | Confirmed
AL-70087 | R-3004 | Daniel Kim | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-13 | 13 | 40 | Confirmed
AL-70098 | R-3005 | Sofia Rossi | Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-01 | 15 | 40 | Confirmed
AL-70109 | R-3005 | Sofia Rossi | Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 17 | 40 | Confirmed
AL-70214 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-15 | 11 | 32 | Confirmed
AL-70101 | R-3005 | Sofia Rossi | Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 13 | 40 | Confirmed
AL-70070 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-10 | 12 | 40 | Confirmed
AL-70078 | R-3004 | Daniel Kim | Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 30 | 40 | Confirmed
AL-70283 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 30 | 40 | Confirmed
AL-70155 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-20 | 20 | 40 | Confirmed
AL-70157 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 16 | 40 | Confirmed
AL-70266 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 22 | 40 | Confirmed
AL-70156 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-07-27 | 16 | 40 | Confirmed
AL-70220 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 17 | 32 | Confirmed
AL-70197 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-22 | 12 | 40 | Confirmed
AL-70148 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-06-29 | 14 | 40 | Confirmed
AL-70324 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 21 | 24 | Confirmed
AL-70253 | R-3011 | Grace Liu | Project Manager | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-17 | 38 | 40 | Confirmed
AL-70262 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 10 | 40 | Confirmed
AL-70229 | R-3011 | Grace Liu | Project Manager | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-01 | 21 | 40 | Confirmed
AL-70034 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-29 | 13 | 40 | Confirmed
AL-70151 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 14 | 40 | Confirmed
AL-70158 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 22 | 40 | Confirmed
AL-70243 | R-3011 | Grace Liu | Project Manager | PRJ-OP-203 | Insurance Claims Automation | 2026-07-13 | 20 | 40 | Confirmed
AL-70342 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 5 | 24 | Confirmed
AL-70160 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-08-10 | 10 | 40 | Confirmed
AL-70250 | R-3011 | Grace Liu | Project Manager | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-03 | 14 | 40 | Confirmed
AL-70343 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 22 | 40 | Confirmed
AL-70272 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 17 | 40 | Confirmed
AL-70149 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 15 | 40 | Confirmed
AL-70203 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-13 | 12 | 40 | Confirmed
AL-70209 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 32 | 40 | Confirmed
AL-70172 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 15 | 40 | Confirmed
AL-70232 | R-3011 | Grace Liu | Project Manager | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 21 | 40 | Confirmed
AL-70053 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 21 | 40 | Confirmed
AL-70269 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-204 | Core Banking API Layer | 2026-07-20 | 13 | 40 | Confirmed
AL-70265 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 13 | 40 | Confirmed
AL-70308 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-29 | 10 | 40 | Confirmed
AL-70205 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-20 | 37 | 40 | Confirmed
AL-70075 | R-3004 | Daniel Kim | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-08 | 13 | 40 | Confirmed
AL-70206 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-07-27 | 35 | 40 | Confirmed
AL-70049 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-204 | Core Banking API Layer | 2026-06-01 | 17 | 40 | Confirmed
AL-70005 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 15 | 40 | Confirmed
AL-70331 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 6 | 24 | Confirmed
AL-70306 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 10 | 40 | Confirmed
AL-70246 | R-3011 | Grace Liu | Project Manager | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 9 | 40 | Confirmed
AL-70241 | R-3011 | Grace Liu | Project Manager | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-06 | 13 | 40 | Confirmed
AL-70174 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 13 | 40 | Confirmed
AL-70168 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 28 | 40 | Confirmed
AL-70077 | R-3004 | Daniel Kim | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 12 | 40 | Confirmed
AL-70166 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-204 | Core Banking API Layer | 2026-06-01 | 17 | 40 | Confirmed
AL-70095 | R-3004 | Daniel Kim | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-10 | 10 | 40 | Confirmed
AL-70244 | R-3011 | Grace Liu | Project Manager | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-13 | 19 | 40 | Confirmed
AL-70305 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 10 | 40 | Confirmed
AL-70022 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 14 | 40 | Confirmed
AL-70255 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 13 | 40 | Confirmed
AL-70189 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-01 | 15 | 40 | Confirmed
AL-70061 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-13 | 38 | 40 | Confirmed
AL-70150 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 13 | 40 | Confirmed
AL-70140 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 14 | 40 | Confirmed
AL-70118 | R-3005 | Sofia Rossi | Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-03 | 20 | 40 | Confirmed
AL-70105 | R-3005 | Sofia Rossi | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 10 | 40 | Confirmed
AL-70248 | R-3011 | Grace Liu | Project Manager | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 18 | 40 | Confirmed
AL-70323 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-17 | 18 | 40 | Confirmed
AL-70032 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 32 | 40 | Confirmed
AL-70361 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 |  | 40 | Confirmed
AL-70162 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 9 | 40 | Confirmed
AL-70031 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 11 | 40 | Confirmed
AL-70211 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 15 | 40 | Confirmed
AL-70165 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 13 | 40 | Confirmed
AL-70230 | R-3011 | Grace Liu | Project Manager | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-01 | 17 | 40 | Confirmed
AL-70329 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 20 | 24 | Confirmed
AL-70133 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-13 | 15 | 40 | Confirmed
AL-70193 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 8 | 40 | Confirmed
AL-70228 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-203 | Insurance Claims Automation | 2026-08-17 | 30 | 32 | Confirmed
AL-70273 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-03 | 17 | 40 | Confirmed
AL-70291 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-20 | 17 | 40 | Confirmed
AL-70136 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 23 | 40 | Confirmed
AL-70315 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 19 | 40 | Confirmed
AL-70184 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-03 | 16 | 40 | Confirmed
AL-70261 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-203 | Insurance Claims Automation | 2026-06-22 | 13 | 40 | Confirmed
AL-70054 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 15 | 40 | Confirmed
AL-70338 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-203 | Insurance Claims Automation | 2026-08-03 | 18 | 24 | Confirmed
AL-70319 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-203 | Insurance Claims Automation | 2026-08-03 | 13 | 40 | Confirmed
AL-70033 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 16 | 40 | Confirmed
AL-70204 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 12 | 40 | Confirmed
AL-70198 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-29 | 33 | 40 | Confirmed
AL-70088 | R-3004 | Daniel Kim | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-20 | 14 | 40 | Confirmed
AL-70117 | R-3005 | Sofia Rossi | Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 17 | 40 | Confirmed
AL-70104 | R-3005 | Sofia Rossi | Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-15 | 18 | 40 | Confirmed
AL-70141 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-17 | 39 | 40 | Confirmed
AL-70217 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 14 | 32 | Confirmed
AL-70276 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-203 | Insurance Claims Automation | 2026-08-17 | 13 | 40 | Confirmed
AL-70063 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-20 | 9 | 40 | Confirmed
AL-70069 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-03 | 14 | 40 | Confirmed
AL-70237 | R-3011 | Grace Liu | Project Manager | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 20 | 40 | Confirmed
AL-70035 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 28 | 40 | Confirmed
AL-70096 | R-3004 | Daniel Kim | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-17 | 14 | 40 | Confirmed
AL-70312 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 17 | 40 | Confirmed
AL-70089 | R-3004 | Daniel Kim | Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 12 | 40 | Confirmed
AL-70330 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 19 | 24 | Confirmed
AL-70277 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-17 | 17 | 40 | Confirmed
AL-70041 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-204 | Core Banking API Layer | 2026-07-27 | 14 | 40 | Confirmed
AL-70268 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-13 | 15 | 40 | Confirmed
AL-70249 | R-3011 | Grace Liu | Project Manager | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-03 | 19 | 40 | Confirmed
AL-70163 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-17 | 10 | 40 | Confirmed
AL-70270 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 18 | 40 | Confirmed
AL-70360 | R-3005 | Sofia Rossi | Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-08-03 | 20 | 40 | Tentative
AL-70128 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 16 | 40 | Confirmed
AL-70344 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-22 | 20 | 40 | Confirmed
AL-70132 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-13 | 11 | 40 | Confirmed
AL-70341 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-17 | 6 | 24 | Confirmed
AL-70131 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-06 | 17 | 40 | Confirmed
AL-70021 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 30 | 40 | Confirmed
AL-70164 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 12 | 40 | Confirmed
AL-70245 | R-3011 | Grace Liu | Project Manager | PRJ-OP-204 | Core Banking API Layer | 2026-07-20 | 30 | 40 | Confirmed
AL-70125 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 17 | 40 | Confirmed
AL-70039 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-204 | Core Banking API Layer | 2026-07-20 | 33 | 40 | Confirmed
AL-70050 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 15 | 40 | Confirmed
AL-70004 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 33 | 40 | Confirmed
AL-70099 | R-3005 | Sofia Rossi | Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-01 | 17 | 40 | Confirmed
AL-70124 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 21 | 40 | Confirmed
AL-70242 | R-3011 | Grace Liu | Project Manager | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 14 | 40 | Confirmed
AL-70028 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-08 | 11 | 40 | Confirmed
AL-70347 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-29 | 20 | 40 | Confirmed
AL-70327 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 10 | 24 | Confirmed
AL-70195 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-06-15 | 13 | 40 | Confirmed
AL-70297 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-08-10 | 32 | 40 | Confirmed
AL-70074 | R-3004 | Daniel Kim | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-01 | 30 | 40 | Confirmed
AL-70126 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-15 | 15 | 40 | Confirmed
AL-70307 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-22 | 9 | 40 | Confirmed
AL-70066 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 7 | 40 | Confirmed
AL-70325 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 20 | 24 | Confirmed
AL-70210 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-17 | 16 | 40 | Confirmed
AL-70353 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-20 | 16 | 32 | Confirmed
AL-70093 | R-3004 | Daniel Kim | Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 12 | 40 | Confirmed
AL-70221 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-203 | Insurance Claims Automation | 2026-07-13 | 14 | 32 | Confirmed
AL-70138 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-203 | Insurance Claims Automation | 2026-08-03 | 33 | 40 | Confirmed
AL-70065 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 12 | 40 | Confirmed
AL-70351 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 14 | 40 | Confirmed
AL-70318 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 13 | 40 | Confirmed
AL-70147 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-22 | 34 | 40 | Confirmed
AL-70007 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 8 | 40 | Confirmed
AL-70145 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-15 | 15 | 40 | Confirmed
AL-70116 | R-3005 | Sofia Rossi | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 12 | 40 | Confirmed
AL-70267 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-203 | Insurance Claims Automation | 2026-07-13 | 13 | 40 | Confirmed
AL-70357 | R-3099 | Unknown Contractor | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 30 | 40 | Confirmed
AL-70332 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-13 | 6 | 24 | Confirmed
AL-70146 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 21 | 40 | Confirmed
AL-70185 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-10 | 16 | 40 | Confirmed
AL-70153 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-13 | 34 | 40 | Confirmed
AL-70121 | R-3005 | Sofia Rossi | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 38 | 40 | Confirmed
AL-70154 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 15 | 40 | Confirmed
AL-70313 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-203 | Insurance Claims Automation | 2026-07-13 | 14 | 40 | Confirmed
AL-70340 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 7 | 24 | Confirmed
AL-70321 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 13 | 40 | Confirmed
AL-70076 | R-3004 | Daniel Kim | Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-08 | 10 | 40 | Confirmed
AL-70178 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-203 | Insurance Claims Automation | 2026-07-20 | 20 | 40 | Confirmed
AL-70073 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-17 | 20 | 40 | Confirmed
AL-70296 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 16 | 40 | Confirmed
AL-70191 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 17 | 40 | Confirmed
AL-70177 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-13 | 32 | 40 | Confirmed
AL-70199 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 10 | 40 | Confirmed
AL-70114 | R-3005 | Sofia Rossi | Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-20 | 12 | 40 | Confirmed
AL-70175 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-06 | 16 | 40 | Confirmed
AL-70303 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-15 | 25 | 40 | Confirmed
AL-70226 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 30 | 32 | Confirmed
AL-70293 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 21 | 40 | Confirmed
AL-70130 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 21 | 40 | Confirmed
AL-70302 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 19 | 40 | Confirmed
AL-70187 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 24 | 40 | Confirmed
AL-70110 | R-3005 | Sofia Rossi | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 15 | 40 | Confirmed
AL-70120 | R-3005 | Sofia Rossi | Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 22 | 40 | Confirmed
AL-70122 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-01 | 37 | 40 | Confirmed
AL-70048 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-17 | 19 | 40 | Confirmed
AL-70335 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-204 | Core Banking API Layer | 2026-07-20 | 12 | 24 | Confirmed
AL-70234 | R-3011 | Grace Liu | Project Manager | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 9 | 40 | Confirmed
AL-70018 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-204 | Core Banking API Layer | 2026-07-27 | 11 | 40 | Confirmed
AL-70350 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 20 | 40 | Confirmed
AL-70218 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 29 | 32 | Confirmed
AL-70264 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-203 | Insurance Claims Automation | 2026-06-29 | 12 | 40 | Confirmed
AL-70356 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 18 | 24 | Confirmed
AL-70260 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 20 | 40 | Confirmed
AL-70259 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-204 | Core Banking API Layer | 2026-06-15 | 34 | 40 | Confirmed
AL-70100 | R-3005 | Sofia Rossi | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 7 | 40 | Confirmed
AL-70202 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-13 | 12 | 40 | Confirmed
AL-70037 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 10 | 40 | Confirmed
AL-70190 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 19 | 40 | Confirmed
AL-70038 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-13 | 11 | 40 | Confirmed
AL-70346 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 22 | 40 | Confirmed
AL-70159 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 18 | 40 | Confirmed
AL-70102 | R-3005 | Sofia Rossi | Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-08 | 8 | 40 | Confirmed
AL-70015 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-20 | 32 | 40 | Confirmed
AL-70285 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 12 | 40 | Confirmed
AL-70358 | R-3005 | Sofia Rossi | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-15 | 20 | 40 | Tentative
AL-70042 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 10 | 40 | Confirmed
AL-70328 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 10 | 24 | Confirmed
AL-70036 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-13 | 7 | 40 | Confirmed
AL-70111 | R-3005 | Sofia Rossi | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 18 | 40 | Confirmed
AL-70355 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-27 | 16 | 32 | Confirmed
AL-70359 | R-3005 | Sofia Rossi | Developer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-13 | 20 | 40 | Tentative
AL-70003 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-204 | Core Banking API Layer | 2026-06-01 | 19 | 40 | Confirmed
AL-70348 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 14 | 40 | Confirmed
AL-70282 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-08 | 19 | 40 | Confirmed
AL-70079 | R-3004 | Daniel Kim | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 20 | 40 | Confirmed
AL-70212 | R-3010 | Ravi Menon | Business Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-06-01 | 25 | 32 | Confirmed
AL-70240 | R-3011 | Grace Liu | Project Manager | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-06 | 10 | 40 | Confirmed
AL-70006 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 16 | 40 | Confirmed
AL-70300 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 20 | 40 | Confirmed
AL-70072 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-17 | 18 | 40 | Confirmed
AL-70194 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 11 | 40 | Confirmed
AL-70103 | R-3005 | Sofia Rossi | Developer | PRJ-OP-204 | Core Banking API Layer | 2026-06-15 | 17 | 40 | Confirmed
AL-70278 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-01 | 11 | 40 | Confirmed
AL-70067 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-27 | 12 | 40 | Confirmed
AL-70143 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-01 | 15 | 40 | Confirmed
AL-70192 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-08 | 19 | 40 | Confirmed
AL-70002 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-01 | 14 | 40 | Confirmed
AL-70188 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 13 | 40 | Confirmed
AL-70208 | R-3009 | Hannah Wright | Business Analyst | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-03 | 15 | 40 | Confirmed
AL-70247 | R-3011 | Grace Liu | Project Manager | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-27 | 12 | 40 | Confirmed
AL-70024 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 24 | 40 | Confirmed
AL-70314 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-20 | 31 | 40 | Confirmed
AL-70142 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-204 | Core Banking API Layer | 2026-06-01 | 17 | 40 | Confirmed
AL-70030 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 11 | 40 | Confirmed
AL-70251 | R-3011 | Grace Liu | Project Manager | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 13 | 40 | Confirmed
AL-70311 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 37 | 40 | Confirmed
AL-70008 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 11 | 40 | Confirmed
AL-70337 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-204 | Core Banking API Layer | 2026-07-27 | 13 | 24 | Confirmed
AL-70170 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-15 | 18 | 40 | Confirmed
AL-70301 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-08 | 12 | 40 | Confirmed
AL-70119 | R-3005 | Sofia Rossi | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-10 | 16 | 40 | Confirmed
AL-70326 | R-3015 | Yuki Tanaka | UX Designer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 20 | 24 | Confirmed
AL-70284 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 14 | 40 | Confirmed
AL-70115 | R-3005 | Sofia Rossi | Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 19 | 40 | Confirmed
AL-70274 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 19 | 40 | Confirmed
AL-70043 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 11 | 40 | Confirmed
AL-70238 | R-3011 | Grace Liu | Project Manager | PRJ-OP-204 | Core Banking API Layer | 2026-06-29 | 17 | 40 | Confirmed
AL-70013 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 38 | 40 | Confirmed
AL-70345 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-22 | 14 | 40 | Confirmed
AL-70288 | R-3013 | Nina Patel | Data Engineer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 35 | 40 | Confirmed
AL-70062 | R-3003 | Priya Nair | Senior Developer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 11 | 40 | Confirmed
AL-70012 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 11 | 40 | Confirmed
AL-70017 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 16 | 40 | Confirmed
AL-70144 | R-3007 | Lena Fischer | QA Analyst | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-08 | 37 | 40 | Confirmed
AL-70181 | R-3008 | Tomas Vega | Data Migration Specialist | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 12 | 40 | Confirmed
AL-70127 | R-3006 | Marcus Bell | QA Lead | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 32 | 40 | Confirmed
AL-70322 | R-3014 | Jack Thompson | DevOps Engineer | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 16 | 40 | Confirmed
AL-70233 | R-3011 | Grace Liu | Project Manager | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-15 | 9 | 40 | Confirmed
AL-70258 | R-3012 | Omar Haddad | Scrum Master | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-08 | 11 | 40 | Confirmed
AL-70040 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 20 | 40 | Confirmed
AL-70362 | R-3002 | Ben Carrow | Senior Developer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 24 | 40 | Confirmed
AL-70083 | R-3004 | Daniel Kim | Developer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 9 | 40 | Confirmed
AL-70019 | R-3001 | Amara Okafor | Solution Architect | PRJ-OP-203 | Insurance Claims Automation | 2026-08-03 | 19 | 40 | Confirmed

## Time & Expense
Time & Expense — logged hours
Logged vs booked. Billable flag drives revenue recognition.
Entry ID | Resource ID | Resource Name | Project ID | Project Name | Week Starting | Logged Hours | Billable | Approval Status
TE-90125 | R-3007 | Lena Fischer | PRJ-OP-204 | Core Banking API Layer | 2026-08-10 | 11 | Billable | Approved
TE-90106 | R-3003 | Priya Nair | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-10 | 12 | Non-billable | Approved
TE-90348 | R-3001 | Amara Okafor | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 32 | Billable | Submitted
TE-90248 | R-3005 | Sofia Rossi | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 33 | Non-billable | Approved
TE-90269 | R-3005 | Sofia Rossi | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 22 | Billable | Approved
TE-90238 | R-3014 | Jack Thompson | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 12 | Billable | Approved
TE-90066 | R-3002 | Ben Carrow | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-10 | 10 | Billable | Approved
TE-90325 | R-3005 | Sofia Rossi | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-10 | 18 | Billable | Approved
TE-90336 | R-3001 | Amara Okafor | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 10 | Billable | Approved
TE-90078 | R-3013 | Nina Patel | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 13 | Billable | Approved
TE-90247 | R-3007 | Lena Fischer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-13 | 34 | Billable | Approved
TE-90060 | R-3015 | Yuki Tanaka | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 18 | Billable | Approved
TE-90254 | R-3008 | Tomas Vega | PRJ-OP-203 | Insurance Claims Automation | 2026-07-20 | 22 | Billable | Approved
TE-90183 | R-3002 | Ben Carrow | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 17 | Billable | Approved
TE-90044 | R-3013 | Nina Patel | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 17 | Billable | Approved
TE-90231 | R-3009 | Hannah Wright | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-17 | 18 | Billable | Approved
TE-90131 | R-3009 | Hannah Wright | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 26 | Billable | Approved
TE-90221 | R-3002 | Ben Carrow | PRJ-OP-203 | Insurance Claims Automation | 2026-06-08 | 11 | Billable | Approved
TE-90171 | R-3006 | Marcus Bell | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-13 | 17 | Billable | Approved
TE-90205 | R-3012 | Omar Haddad | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 17 | Non-billable | Approved
TE-90025 | R-3006 | Marcus Bell | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-08 | 13 | Billable | Approved
TE-90103 | R-3005 | Sofia Rossi | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 15 | Billable | Approved
TE-90223 | R-3015 | Yuki Tanaka | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 9 | Billable | Approved
TE-90200 | R-3012 | Omar Haddad | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-17 | 17 | Non-billable | Approved
TE-90145 | R-3011 | Grace Liu | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 9 | Billable | Approved
TE-90165 | R-3007 | Lena Fischer | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 9 | Billable | Approved
TE-90268 | R-3005 | Sofia Rossi | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 15 | Billable | Approved
TE-90058 | R-3015 | Yuki Tanaka | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 9 | Billable | Approved
TE-90070 | R-3013 | Nina Patel | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-13 | 16 | Non-billable | Approved
TE-90023 | R-3002 | Ben Carrow | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 6 | Billable | Approved
TE-90232 | R-3010 | Ravi Menon | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-20 | 16 | Billable | Approved
TE-90095 | R-3006 | Marcus Bell | PRJ-OP-204 | Core Banking API Layer | 2026-08-10 | 20 | Billable | Approved
TE-90267 | R-3008 | Tomas Vega | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 20 | Billable | Approved
TE-90008 | R-3009 | Hannah Wright | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 14 | Billable | Approved
TE-90063 | R-3005 | Sofia Rossi | PRJ-OP-204 | Core Banking API Layer | 2026-06-29 | 15 | Billable | Approved
TE-90069 | R-3014 | Jack Thompson | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 11 | Non-billable | Approved
TE-90277 | R-3012 | Omar Haddad | PRJ-OP-203 | Insurance Claims Automation | 2026-06-29 | 13 | Billable | Approved
TE-90024 | R-3004 | Daniel Kim | PRJ-OP-204 | Core Banking API Layer | 2026-08-10 | 13 | Billable | Approved
TE-90152 | R-3011 | Grace Liu | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-13 | 19 | Billable | Approved
TE-90288 | R-3005 | Sofia Rossi | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-08 | 8 | Billable | Approved
TE-90190 | R-3010 | Ravi Menon | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 12 | Billable | Approved
TE-90323 | R-3008 | Tomas Vega | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-15 | 19 | Billable | Approved
TE-90099 | R-3006 | Marcus Bell | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-20 | 14 | Non-billable | Approved
TE-90161 | R-3005 | Sofia Rossi | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 9 | Billable | Approved
TE-90203 | R-3011 | Grace Liu | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-03 | 17 | Billable | Approved
TE-90230 | R-3015 | Yuki Tanaka | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 20 | Non-billable | Approved
TE-90299 | R-3004 | Daniel Kim | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 17 | Non-billable | Approved
TE-90293 | R-3002 | Ben Carrow | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-13 | 6 | Billable | Approved
TE-90003 | R-3006 | Marcus Bell | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-27 | 34 | Billable | Approved
TE-90158 | R-3007 | Lena Fischer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 13 | Billable | Approved
TE-90349 | R-3013 | Nina Patel | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-20 | 28 | Billable | Approved
TE-90340 | R-3006 | Marcus Bell | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 30 | Billable | Approved
TE-90210 | R-3006 | Marcus Bell | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-06 | 19 | Billable | Approved
TE-90137 | R-3014 | Jack Thompson | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-29 | 11 | Billable | Approved
TE-90076 | R-3010 | Ravi Menon | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 13 | Billable | Approved
TE-90201 | R-3002 | Ben Carrow | PRJ-OP-204 | Core Banking API Layer | 2026-07-27 | 13 | Billable | Approved
TE-90119 | R-3011 | Grace Liu | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-01 | 18 | Billable | Approved
TE-90261 | R-3008 | Tomas Vega | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-06 | 17 | Billable | Approved
TE-90138 | R-3009 | Hannah Wright | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-20 | 40 | Billable | Approved
TE-90134 | R-3003 | Priya Nair | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 18 | Billable | Approved
TE-90105 | R-3005 | Sofia Rossi | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 14 | Billable | Approved
TE-90244 | R-3015 | Yuki Tanaka | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-13 | 6 | Non-billable | Approved
TE-90240 | R-3001 | Amara Okafor | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 7 | Billable | Approved
TE-90275 | R-3003 | Priya Nair | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 19 | Billable | Approved
TE-90280 | R-3012 | Omar Haddad | PRJ-OP-204 | Core Banking API Layer | 2026-06-15 | 31 | Billable | Approved
TE-90055 | R-3004 | Daniel Kim | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-20 | 11 | Billable | Approved
TE-90045 | R-3003 | Priya Nair | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 18 | Billable | Approved
TE-90226 | R-3004 | Daniel Kim | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-01 | 25 | Billable | Approved
TE-90162 | R-3011 | Grace Liu | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 18 | Billable | Approved
TE-90222 | R-3003 | Priya Nair | PRJ-OP-203 | Insurance Claims Automation | 2026-06-29 | 22 | Billable | Approved
TE-90065 | R-3005 | Sofia Rossi | PRJ-OP-203 | Insurance Claims Automation | 2026-06-22 | 10 | Billable | Approved
TE-90114 | R-3009 | Hannah Wright | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-22 | 13 | Billable | Approved
TE-90321 | R-3001 | Amara Okafor | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 10 | Non-billable | Approved
TE-90217 | R-3001 | Amara Okafor | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 36 | Billable | Approved
TE-90282 | R-3009 | Hannah Wright | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-13 | 13 | Non-billable | Approved
TE-90175 | R-3013 | Nina Patel | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-20 | 15 | Billable | Approved
TE-90271 | R-3002 | Ben Carrow | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-17 | 17 | Non-billable | Approved
TE-90021 | R-3007 | Lena Fischer | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 10 | Billable | Approved
TE-90051 | R-3004 | Daniel Kim | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-13 | 17 | Billable | Approved
TE-90259 | R-3009 | Hannah Wright | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 10 | Non-billable | Approved
TE-90143 | R-3015 | Yuki Tanaka | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 6 | Non-billable | Approved
TE-90091 | R-3005 | Sofia Rossi | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-20 | 17 | Billable | Approved
TE-90301 | R-3011 | Grace Liu | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-06 | 11 | Billable | Approved
TE-90168 | R-3007 | Lena Fischer | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 11 | Billable | Approved
TE-90173 | R-3010 | Ravi Menon | PRJ-OP-203 | Insurance Claims Automation | 2026-08-17 | 31 | Billable | Approved
TE-90204 | R-3007 | Lena Fischer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-17 | 9 | Billable | Approved
TE-90050 | R-3002 | Ben Carrow | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-10 | 21 | Billable | Approved
TE-90088 | R-3012 | Omar Haddad | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 12 | Billable | Approved
TE-90250 | R-3014 | Jack Thompson | PRJ-OP-203 | Insurance Claims Automation | 2026-07-13 | 14 | Billable | Approved
TE-90185 | R-3009 | Hannah Wright | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-29 | 30 | Billable | Approved
TE-90335 | R-3003 | Priya Nair | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 10 | Billable | Approved
TE-90343 | R-3012 | Omar Haddad | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-08 | 10 | Billable | Approved
TE-90133 | R-3011 | Grace Liu | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 20 | Billable | Approved
TE-90274 | R-3001 | Amara Okafor | PRJ-OP-204 | Core Banking API Layer | 2026-07-27 | 11 | Billable | Approved
TE-90234 | R-3010 | Ravi Menon | PRJ-OP-203 | Insurance Claims Automation | 2026-07-13 | 12 | Billable | Approved
TE-90213 | R-3011 | Grace Liu | PRJ-OP-204 | Core Banking API Layer | 2026-07-20 | 26 | Billable | Approved
TE-90284 | R-3009 | Hannah Wright | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 18 | Billable | Approved
TE-90028 | R-3014 | Jack Thompson | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 18 | Billable | Approved
TE-90179 | R-3012 | Omar Haddad | PRJ-OP-203 | Insurance Claims Automation | 2026-06-22 | 14 | Billable | Approved
TE-90236 | R-3003 | Priya Nair | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 11 | Billable | Approved
TE-90178 | R-3008 | Tomas Vega | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-03 | 18 | Billable | Approved
TE-90346 | R-3004 | Daniel Kim | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 8 | Non-billable | Approved
TE-90331 | R-3011 | Grace Liu | PRJ-OP-204 | Core Banking API Layer | 2026-06-29 | 16 | Non-billable | Approved
TE-90257 | R-3009 | Hannah Wright | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 18 | Billable | Approved
TE-90043 | R-3003 | Priya Nair | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-08 | 16 | Billable | Approved
TE-90279 | R-3012 | Omar Haddad | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 19 | Billable | Approved
TE-90251 | R-3015 | Yuki Tanaka | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 6 | Billable | Approved
TE-90048 | R-3003 | Priya Nair | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-06 | 18 | Billable | Approved
TE-90113 | R-3010 | Ravi Menon | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 14 | Non-billable | Approved
TE-90122 | R-3007 | Lena Fischer | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 19 | Billable | Approved
TE-90207 | R-3003 | Priya Nair | PRJ-OP-203 | Insurance Claims Automation | 2026-06-22 | 21 | Billable | Approved
TE-90038 | R-3015 | Yuki Tanaka | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-13 | 6 | Billable | Approved
TE-90046 | R-3004 | Daniel Kim | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 11 | Billable | Approved
TE-90246 | R-3008 | Tomas Vega | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-10 | 14 | Billable | Approved
TE-90184 | R-3009 | Hannah Wright | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 11 | Non-billable | Approved
TE-90053 | R-3011 | Grace Liu | PRJ-OP-203 | Insurance Claims Automation | 2026-06-08 | 20 | Billable | Approved
TE-90186 | R-3004 | Daniel Kim | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-20 | 15 | Billable | Approved
TE-90314 | R-3011 | Grace Liu | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-27 | 10 | Billable | Approved
TE-90057 | R-3004 | Daniel Kim | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-27 | 42 | Billable | Approved
TE-90276 | R-3010 | Ravi Menon | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 32 | Billable | Approved
TE-90329 | R-3012 | Omar Haddad | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 16 | Billable | Approved
TE-90155 | R-3012 | Omar Haddad | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 14 | Billable | Approved
TE-90170 | R-3015 | Yuki Tanaka | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 22 | Billable | Approved
TE-90004 | R-3009 | Hannah Wright | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 12 | Billable | Approved
TE-90093 | R-3014 | Jack Thompson | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-01 | 18 | Billable | Approved
TE-90215 | R-3002 | Ben Carrow | PRJ-OP-204 | Core Banking API Layer | 2026-07-20 | 31 | Billable | Approved
TE-90263 | R-3010 | Ravi Menon | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 33 | Billable | Approved
TE-90327 | R-3013 | Nina Patel | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 14 | Billable | Approved
TE-90180 | R-3003 | Priya Nair | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 13 | Billable | Approved
TE-90258 | R-3008 | Tomas Vega | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-13 | 35 | Billable | Approved
TE-90087 | R-3013 | Nina Patel | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-03 | 12 | Billable | Approved
TE-90345 | R-3002 | Ben Carrow | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 20 | Billable | Approved
TE-90039 | R-3007 | Lena Fischer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-10 | 8 | Billable | Approved
TE-90151 | R-3004 | Daniel Kim | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-10 | 10 | Billable | Approved
TE-90266 | R-3014 | Jack Thompson | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 19 | Billable | Approved
TE-90255 | R-3003 | Priya Nair | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-17 | 19 | Billable | Approved
TE-90012 | R-3004 | Daniel Kim | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 10 | Non-billable | Approved
TE-90243 | R-3012 | Omar Haddad | PRJ-OP-203 | Insurance Claims Automation | 2026-07-13 | 11 | Billable | Approved
TE-90092 | R-3004 | Daniel Kim | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 16 | Non-billable | Approved
TE-90322 | R-3015 | Yuki Tanaka | PRJ-OP-204 | Core Banking API Layer | 2026-07-27 | 11 | Billable | Approved
TE-90079 | R-3008 | Tomas Vega | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 18 | Billable | Approved
TE-90172 | R-3009 | Hannah Wright | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 9 | Billable | Approved
TE-90049 | R-3003 | Priya Nair | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-08 | 18 | Billable | Approved
TE-90163 | R-3014 | Jack Thompson | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-17 | 17 | Billable | Approved
TE-90294 | R-3005 | Sofia Rossi | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 19 | Non-billable | Approved
TE-90139 | R-3004 | Daniel Kim | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-08 | 14 | Billable | Approved
TE-90283 | R-3002 | Ben Carrow | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 11 | Non-billable | Approved
TE-90237 | R-3003 | Priya Nair | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 12 | Billable | Approved
TE-90209 | R-3015 | Yuki Tanaka | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-17 | 7 | Billable | Approved
TE-90181 | R-3015 | Yuki Tanaka | PRJ-OP-203 | Insurance Claims Automation | 2026-08-03 | 15 | Billable | Approved
TE-90022 | R-3012 | Omar Haddad | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-01 | 18 | Billable | Approved
TE-90075 | R-3001 | Amara Okafor | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 19 | Non-billable | Approved
TE-90228 | R-3014 | Jack Thompson | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-22 | 7 | Billable | Approved
TE-90037 | R-3008 | Tomas Vega | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 14 | Billable | Approved
TE-90262 | R-3014 | Jack Thompson | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-15 | 24 | Billable | Approved
TE-90148 | R-3008 | Tomas Vega | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 25 | Billable | Approved
TE-90300 | R-3010 | Ravi Menon | PRJ-OP-204 | Core Banking API Layer | 2026-06-01 | 23 | Non-billable | Approved
TE-90290 | R-3013 | Nina Patel | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 13 | Billable | Approved
TE-90309 | R-3007 | Lena Fischer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-01 | 14 | Non-billable | Approved
TE-90002 | R-3012 | Omar Haddad | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 34 | Non-billable | Approved
TE-90014 | R-3015 | Yuki Tanaka | PRJ-OP-203 | Insurance Claims Automation | 2026-07-20 | 9 | Billable | Approved
TE-90239 | R-3007 | Lena Fischer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-22 | 30 | Non-billable | Approved
TE-90141 | R-3003 | Priya Nair | PRJ-OP-204 | Core Banking API Layer | 2026-06-01 | 15 | Billable | Approved
TE-90081 | R-3004 | Daniel Kim | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-17 | 15 | Non-billable | Approved
TE-90136 | R-3012 | Omar Haddad | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 13 | Billable | Approved
TE-90176 | R-3006 | Marcus Bell | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 23 | Billable | Approved
TE-90056 | R-3001 | Amara Okafor | PRJ-OP-203 | Insurance Claims Automation | 2026-08-17 | 18 | Billable | Approved
TE-90166 | R-3002 | Ben Carrow | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 11 | Billable | Approved
TE-90241 | R-3007 | Lena Fischer | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-15 | 15 | Billable | Approved
TE-90011 | R-3010 | Ravi Menon | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-15 | 14 | Billable | Approved
TE-90073 | R-3014 | Jack Thompson | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 9 | Billable | Approved
TE-90198 | R-3004 | Daniel Kim | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 10 | Billable | Approved
TE-90019 | R-3008 | Tomas Vega | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 17 | Billable | Approved
TE-90072 | R-3008 | Tomas Vega | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-01 | 13 | Non-billable | Approved
TE-90154 | R-3001 | Amara Okafor | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 15 | Billable | Approved
TE-90147 | R-3008 | Tomas Vega | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 14 | Non-billable | Approved
TE-90146 | R-3011 | Grace Liu | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-06 | 12 | Billable | Approved
TE-90338 | R-3007 | Lena Fischer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-08 | 31 | Non-billable | Approved
TE-90189 | R-3006 | Marcus Bell | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-17 | 40 | Billable | Approved
TE-90308 | R-3003 | Priya Nair | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-27 | 11 | Billable | Approved
TE-90303 | R-3014 | Jack Thompson | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 20 | Billable | Approved
TE-90086 | R-3004 | Daniel Kim | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 19 | Billable | Approved
TE-90195 | R-3002 | Ben Carrow | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 26 | Non-billable | Approved
TE-90032 | R-3011 | Grace Liu | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-10 | 16 | Non-billable | Approved
TE-90031 | R-3010 | Ravi Menon | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 22 | Billable | Approved
TE-90253 | R-3004 | Daniel Kim | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-08 | 10 | Non-billable | Approved
TE-90132 | R-3008 | Tomas Vega | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 12 | Non-billable | Approved
TE-90188 | R-3005 | Sofia Rossi | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-15 | 20 | Billable | Approved
TE-90150 | R-3008 | Tomas Vega | PRJ-OP-204 | Core Banking API Layer | 2026-06-01 | 17 | Billable | Approved
TE-90047 | R-3013 | Nina Patel | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 9 | Billable | Approved
TE-90085 | R-3013 | Nina Patel | PRJ-OP-204 | Core Banking API Layer | 2026-07-20 | 14 | Non-billable | Approved
TE-90292 | R-3015 | Yuki Tanaka | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 9 | Billable | Approved
TE-90033 | R-3009 | Hannah Wright | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-03 | 13 | Billable | Approved
TE-90333 | R-3003 | Priya Nair | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-22 | 13 | Billable | Approved
TE-90034 | R-3012 | Omar Haddad | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-10 | 17 | Billable | Approved
TE-90159 | R-3006 | Marcus Bell | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 13 | Billable | Approved
TE-90116 | R-3015 | Yuki Tanaka | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 19 | Billable | Approved
TE-90347 | R-3001 | Amara Okafor | PRJ-OP-203 | Insurance Claims Automation | 2026-08-03 | 17 | Billable | Approved
TE-90108 | R-3013 | Nina Patel | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 33 | Billable | Approved
TE-90090 | R-3012 | Omar Haddad | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 10 | Non-billable | Approved
TE-90187 | R-3005 | Sofia Rossi | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 18 | Billable | Approved
TE-90124 | R-3015 | Yuki Tanaka | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 4 | Billable | Approved
TE-90153 | R-3014 | Jack Thompson | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 9 | Billable | Approved
TE-90305 | R-3009 | Hannah Wright | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 11 | Billable | Approved
TE-90219 | R-3006 | Marcus Bell | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 18 | Billable | Approved
TE-90337 | R-3001 | Amara Okafor | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 15 | Non-billable | Approved
TE-90121 | R-3007 | Lena Fischer | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 14 | Billable | Approved
TE-90109 | R-3007 | Lena Fischer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-20 | 21 | Billable | Approved
TE-90067 | R-3003 | Priya Nair | PRJ-OP-203 | Insurance Claims Automation | 2026-07-20 | 10 | Billable | Approved
TE-90193 | R-3003 | Priya Nair | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-03 | 12 | Billable | Approved
TE-90169 | R-3011 | Grace Liu | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-01 | 18 | Billable | Approved
TE-90071 | R-3009 | Hannah Wright | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 14 | Billable | Approved
TE-90127 | R-3003 | Priya Nair | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-22 | 20 | Billable | Approved
TE-90233 | R-3004 | Daniel Kim | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 13 | Billable | Approved
TE-90074 | R-3013 | Nina Patel | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 13 | Billable | Approved
TE-90068 | R-3002 | Ben Carrow | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-01 | 12 | Billable | Approved
TE-90111 | R-3012 | Omar Haddad | PRJ-OP-204 | Core Banking API Layer | 2026-07-06 | 20 | Billable | Approved
TE-90225 | R-3013 | Nina Patel | PRJ-OP-204 | Core Banking API Layer | 2026-08-10 | 33 | Billable | Approved
TE-90061 | R-3004 | Daniel Kim | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-06 | 18 | Billable | Approved
TE-90009 | R-3012 | Omar Haddad | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-08 | 12 | Billable | Approved
TE-90174 | R-3012 | Omar Haddad | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-03 | 18 | Non-billable | Approved
TE-90064 | R-3004 | Daniel Kim | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 25 | Non-billable | Approved
TE-90199 | R-3015 | Yuki Tanaka | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 21 | Billable | Approved
TE-90027 | R-3014 | Jack Thompson | PRJ-OP-204 | Core Banking API Layer | 2026-08-10 | 18 | Billable | Approved
TE-90005 | R-3006 | Marcus Bell | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 14 | Billable | Approved
TE-90212 | R-3007 | Lena Fischer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 12 | Billable | Approved
TE-90220 | R-3011 | Grace Liu | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 12 | Billable | Approved
TE-90214 | R-3006 | Marcus Bell | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 18 | Billable | Approved
TE-90310 | R-3009 | Hannah Wright | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-08 | 21 | Billable | Approved
TE-90273 | R-3011 | Grace Liu | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 9 | Billable | Approved
TE-90326 | R-3015 | Yuki Tanaka | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 21 | Billable | Approved
TE-90123 | R-3011 | Grace Liu | PRJ-OP-203 | Insurance Claims Automation | 2026-07-13 | 18 | Billable | Approved
TE-90016 | R-3001 | Amara Okafor | PRJ-OP-204 | Core Banking API Layer | 2026-06-22 | 12 | Non-billable | Approved
TE-90102 | R-3005 | Sofia Rossi | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-01 | 15 | Billable | Approved
TE-90126 | R-3011 | Grace Liu | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-03 | 14 | Non-billable | Approved
TE-90208 | R-3006 | Marcus Bell | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-13 | 10 | Non-billable | Approved
TE-90013 | R-3011 | Grace Liu | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 17 | Billable | Approved
TE-90341 | R-3014 | Jack Thompson | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 18 | Billable | Approved
TE-90312 | R-3008 | Tomas Vega | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 13 | Billable | Approved
TE-90080 | R-3013 | Nina Patel | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-01 | 10 | Billable | Approved
TE-90320 | R-3014 | Jack Thompson | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 37 | Billable | Approved
TE-90192 | R-3003 | Priya Nair | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-20 | 9 | Non-billable | Approved
TE-90110 | R-3007 | Lena Fischer | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 17 | Billable | Approved
TE-90227 | R-3006 | Marcus Bell | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-15 | 16 | Billable | Approved
TE-90252 | R-3014 | Jack Thompson | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 13 | Billable | Approved
TE-90270 | R-3006 | Marcus Bell | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-01 | 34 | Billable | Approved
TE-90015 | R-3005 | Sofia Rossi | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 34 | Billable | Approved
TE-90036 | R-3013 | Nina Patel | PRJ-OP-203 | Insurance Claims Automation | 2026-06-29 | 41 | Billable | Approved
TE-90007 | R-3006 | Marcus Bell | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 11 | Billable | Approved
TE-90298 | R-3013 | Nina Patel | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-08 | 18 | Billable | Approved
TE-90094 | R-3002 | Ben Carrow | PRJ-OP-202 | Wealth Platform Data Migration | 2026-08-03 | 9 | Billable | Approved
TE-90084 | R-3008 | Tomas Vega | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 8 | Billable | Approved
TE-90129 | R-3007 | Lena Fischer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 13 | Billable | Approved
TE-90202 | R-3012 | Omar Haddad | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-13 | 14 | Billable | Approved
TE-90317 | R-3007 | Lena Fischer | PRJ-OP-204 | Core Banking API Layer | 2026-06-01 | 14 | Billable | Approved
TE-90135 | R-3012 | Omar Haddad | PRJ-OP-204 | Core Banking API Layer | 2026-07-20 | 12 | Non-billable | Approved
TE-90249 | R-3007 | Lena Fischer | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 12 | Billable | Approved
TE-90289 | R-3001 | Amara Okafor | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-20 | 32 | Billable | Approved
TE-90077 | R-3001 | Amara Okafor | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 11 | Billable | Approved
TE-90318 | R-3002 | Ben Carrow | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 11 | Billable | Approved
TE-90197 | R-3014 | Jack Thompson | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 15 | Billable | Approved
TE-90206 | R-3006 | Marcus Bell | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 14 | Billable | Approved
TE-90260 | R-3005 | Sofia Rossi | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-20 | 11 | Billable | Approved
TE-90295 | R-3010 | Ravi Menon | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-27 | 14 | Billable | Approved
TE-90191 | R-3012 | Omar Haddad | PRJ-OP-203 | Insurance Claims Automation | 2026-08-17 | 12 | Billable | Approved
TE-90042 | R-3002 | Ben Carrow | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 13 | Billable | Approved
TE-90319 | R-3011 | Grace Liu | PRJ-OP-203 | Insurance Claims Automation | 2026-08-10 | 13 | Billable | Approved
TE-90297 | R-3003 | Priya Nair | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 14 | Non-billable | Approved
TE-90130 | R-3009 | Hannah Wright | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-13 | 12 | Billable | Approved
TE-90272 | R-3015 | Yuki Tanaka | PRJ-OP-204 | Core Banking API Layer | 2026-07-20 | 12 | Non-billable | Approved
TE-90120 | R-3002 | Ben Carrow | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-29 | 13 | Billable | Approved
TE-90196 | R-3004 | Daniel Kim | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-17 | 13 | Non-billable | Approved
TE-90315 | R-3002 | Ben Carrow | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 25 | Billable | Approved
TE-90291 | R-3002 | Ben Carrow | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 9 | Billable | Approved
TE-90059 | R-3001 | Amara Okafor | PRJ-OP-204 | Core Banking API Layer | 2026-07-13 | 32 | Billable | Approved
TE-90182 | R-3014 | Jack Thompson | PRJ-OP-203 | Insurance Claims Automation | 2026-08-03 | 11 | Billable | Approved
TE-90017 | R-3003 | Priya Nair | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-03 | 16 | Billable | Approved
TE-90096 | R-3014 | Jack Thompson | PRJ-OP-204 | Core Banking API Layer | 2026-06-15 | 14 | Billable | Approved
TE-90245 | R-3007 | Lena Fischer | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 21 | Billable | Approved
TE-90098 | R-3013 | Nina Patel | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 17 | Billable | Approved
TE-90229 | R-3003 | Priya Nair | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 6 | Billable | Approved
TE-90115 | R-3007 | Lena Fischer | PRJ-OP-204 | Core Banking API Layer | 2026-06-29 | 15 | Billable | Approved
TE-90118 | R-3012 | Omar Haddad | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 10 | Billable | Approved
TE-90339 | R-3008 | Tomas Vega | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 10 | Billable | Approved
TE-90052 | R-3010 | Ravi Menon | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 22 | Billable | Approved
TE-90040 | R-3008 | Tomas Vega | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 14 | Billable | Approved
TE-90224 | R-3009 | Hannah Wright | PRJ-OP-204 | Core Banking API Layer | 2026-06-15 | 11 | Non-billable | Approved
TE-90128 | R-3012 | Omar Haddad | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 18 | Billable | Approved
TE-90316 | R-3014 | Jack Thompson | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-20 | 33 | Non-billable | Approved
TE-90104 | R-3010 | Ravi Menon | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-15 | 12 | Non-billable | Approved
TE-90311 | R-3001 | Amara Okafor | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-01 | 15 | Non-billable | Approved
TE-90304 | R-3003 | Priya Nair | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-17 | 17 | Billable | Approved
TE-90006 | R-3008 | Tomas Vega | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 22 | Billable | Approved
TE-90054 | R-3010 | Ravi Menon | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-08 | 24 | Billable | Approved
TE-90041 | R-3005 | Sofia Rossi | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 8 | Non-billable | Approved
TE-90062 | R-3010 | Ravi Menon | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 28 | Billable | Approved
TE-90018 | R-3010 | Ravi Menon | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 25 | Billable | Approved
TE-90328 | R-3005 | Sofia Rossi | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-27 | 16 | Billable | Approved
TE-90344 | R-3002 | Ben Carrow | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 22 | Billable | Approved
TE-90334 | R-3013 | Nina Patel | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-06 | 32 | Billable | Approved
TE-90100 | R-3013 | Nina Patel | PRJ-OP-204 | Core Banking API Layer | 2026-08-17 | 33 | Non-billable | Approved
TE-90167 | R-3009 | Hannah Wright | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-17 | 13 | Billable | Approved
TE-90242 | R-3005 | Sofia Rossi | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 11 | Billable | Approved
TE-90112 | R-3007 | Lena Fischer | PRJ-OP-204 | Core Banking API Layer | 2026-07-27 | 16 | Billable | Approved
TE-90156 | R-3009 | Hannah Wright | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-01 | 15 | Billable | Approved
TE-90287 | R-3007 | Lena Fischer | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 16 | Billable | Approved
TE-90157 | R-3003 | Priya Nair | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-07-13 | 39 | Billable | Approved
TE-90030 | R-3014 | Jack Thompson | PRJ-OP-203 | Insurance Claims Automation | 2026-06-29 | 12 | Billable | Approved
TE-90177 | R-3014 | Jack Thompson | PRJ-OP-203 | Insurance Claims Automation | 2026-07-27 | 17 | Billable | Approved
TE-90140 | R-3009 | Hannah Wright | PRJ-OP-204 | Core Banking API Layer | 2026-07-27 | 35 | Billable | Approved
TE-90235 | R-3006 | Marcus Bell | PRJ-OP-203 | Insurance Claims Automation | 2026-08-03 | 36 | Billable | Approved
TE-90306 | R-3005 | Sofia Rossi | PRJ-OP-204 | Core Banking API Layer | 2026-06-15 | 16 | Non-billable | Approved
TE-90082 | R-3008 | Tomas Vega | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-20 | 12 | Non-billable | Approved
TE-90302 | R-3001 | Amara Okafor | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-15 | 14 | Non-billable | Approved
TE-90144 | R-3014 | Jack Thompson | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 9 | Non-billable | Approved
TE-90278 | R-3015 | Yuki Tanaka | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-29 | 16 | Billable | Approved
TE-90194 | R-3011 | Grace Liu | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 21 | Billable | Approved
TE-90026 | R-3011 | Grace Liu | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 14 | Billable | Approved
TE-90029 | R-3008 | Tomas Vega | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-22 | 16 | Billable | Approved
TE-90285 | R-3002 | Ben Carrow | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-07-13 | 9 | Billable | Approved
TE-90256 | R-3013 | Nina Patel | PRJ-OP-204 | Core Banking API Layer | 2026-08-03 | 14 | Billable | Approved
TE-90281 | R-3005 | Sofia Rossi | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 8 | Billable | Approved
TE-90218 | R-3005 | Sofia Rossi | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-01 | 18 | Billable | Approved
TE-90035 | R-3001 | Amara Okafor | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 15 | Billable | Approved
TE-90211 | R-3001 | Amara Okafor | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-10 | 28 | Billable | Approved
TE-90160 | R-3005 | Sofia Rossi | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-08-03 | 19 | Billable | Approved
TE-90332 | R-3001 | Amara Okafor | PRJ-OP-202 | Wealth Platform Data Migration | 2026-07-06 | 38 | Non-billable | Approved
TE-90216 | R-3003 | Priya Nair | PRJ-OP-203 | Insurance Claims Automation | 2026-06-01 | 13 | Billable | Approved
TE-90286 | R-3003 | Priya Nair | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-29 | 23 | Billable | Approved
TE-90101 | R-3004 | Daniel Kim | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-13 | 12 | Billable | Approved
TE-90010 | R-3002 | Ben Carrow | PRJ-OP-204 | Core Banking API Layer | 2026-06-15 | 11 | Billable | Approved
TE-90089 | R-3001 | Amara Okafor | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-29 | 10 | Billable | Approved
TE-90265 | R-3006 | Marcus Bell | PRJ-OP-203 | Insurance Claims Automation | 2026-07-06 | 18 | Billable | Approved
TE-90164 | R-3002 | Ben Carrow | PRJ-OP-202 | Wealth Platform Data Migration | 2026-06-22 | 34 | Billable | Approved
TE-90020 | R-3011 | Grace Liu | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-15 | 10 | Billable | Approved
TE-90142 | R-3001 | Amara Okafor | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 13 | Billable | Approved
TE-90307 | R-3013 | Nina Patel | PRJ-OP-201 | Retail Bank Mobile App Rollout | 2026-06-01 | 12 | Billable | Approved
TE-90117 | R-3011 | Grace Liu | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-17 | 34 | Non-billable | Approved
TE-90296 | R-3001 | Amara Okafor | PRJ-OP-204 | Core Banking API Layer | 2026-06-01 | 21 | Non-billable | Approved
TE-90313 | R-3009 | Hannah Wright | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-08-03 | 14 | Billable | Approved
TE-90149 | R-3004 | Daniel Kim | PRJ-OP-204 | Core Banking API Layer | 2026-06-08 | 13 | Non-billable | Approved
TE-90324 | R-3014 | Jack Thompson | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-06-08 | 13 | Billable | Approved
TE-90330 | R-3002 | Ben Carrow | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-08-03 | 10 | Billable | Approved
TE-90342 | R-3011 | Grace Liu | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-15 | 10 | Billable | Approved
TE-90083 | R-3008 | Tomas Vega | PRJ-OP-204 | Core Banking API Layer | 2026-06-29 | 24 | Non-billable | Approved
TE-90107 | R-3004 | Daniel Kim | PRJ-OP-203 | Insurance Claims Automation | 2026-06-15 | 32 | Billable | Approved
TE-90264 | R-3013 | Nina Patel | PRJ-OP-206 | Payments Fraud Model Uplift | 2026-07-27 | 22 | Non-billable | Approved
TE-90097 | R-3002 | Ben Carrow | PRJ-OP-205 | Regulatory Reporting Dashboard | 2026-06-08 | 10 | Billable | Approved

## Capacity Dashboard
Resource Capacity & Utilisation
Weekly utilisation per resource. RED = over 100%. The portfolio average hides the peaks.
Resource | Cap | 06-01 | 06-08 | 06-15 | 06-22 | 06-29 | 07-06 | 07-13 | 07-20 | 07-27 | 08-03 | 08-10 | 08-17 | Peak | Avg
Amara Okafor | 40 | 82.5% | 82.5% | 77.5% | 80% | 90% | 95% | 77.5% | 80% | 97.5% | 97.5% | 75% | 80% | 97.5% | 84.58%
Ben Carrow | 40 | 157.5% | 72.5% | 85% | 80% | 72.5% | 70% | 70% | 82.5% | 85% | 72.5% | 72.5% | 82.5% | 157.5% | 83.54%
Priya Nair | 40 | 80% | 82.5% | 90% | 140% | 140% | 140% | 95% | 75% | 77.5% | 72.5% | 72.5% | 95% | 140% | 96.67%
Daniel Kim | 40 | 75% | 87.5% | 75% | 95% | 80% | 80% | 75% | 90% | 95% | 72.5% | 85% | 72.5% | 95% | 81.88%
Sofia Rossi | 40 | 80% | 70% | 87.5% | 70% | 82.5% | 82.5% | 92.5% | 72.5% | 77.5% | 92.5% | 95% | 95% | 95% | 83.12%
Marcus Bell | 40 | 92.5% | 92.5% | 80% | 80% | 75% | 95% | 95% | 92.5% | 87.5% | 82.5% | 85% | 97.5% | 97.5% | 87.92%
Lena Fischer | 40 | 80% | 92.5% | 90% | 85% | 72.5% | 95% | 85% | 87.5% | 80% | 100% | 72.5% | 87.5% | 100% | 85.62%
Tomas Vega | 40 | 82.5% | 70% | 87.5% | 77.5% | 87.5% | 80% | 80% | 82.5% | 85% | 90% | 80% | 92.5% | 92.5% | 82.92%
Hannah Wright | 40 | 85% | 90% | 80% | 72.5% | 82.5% | 95% | 90% | 92.5% | 87.5% | 72.5% | 80% | 77.5% | 95% | 83.75%
Ravi Menon | 32 | 78.1% | 84.4% | 78.1% | 84.4% | 90.6% | 71.9% | 96.9% | 125% | 125% | 93.8% | 90.6% | 93.8% | 125% | 92.72%
Grace Liu | 40 | 95% | 97.5% | 70% | 92.5% | 85% | 92.5% | 97.5% | 75% | 97.5% | 82.5% | 75% | 95% | 97.5% | 87.92%
Omar Haddad | 40 | 82.5% | 82.5% | 85% | 82.5% | 92.5% | 87.5% | 70% | 77.5% | 80% | 85% | 95% | 75% | 95% | 82.92%
Nina Patel | 40 | 82.5% | 95% | 75% | 90% | 92.5% | 87.5% | 70% | 80% | 95% | 70% | 80% | 80% | 95% | 83.12%
Jack Thompson | 40 | 97.5% | 77.5% | 95% | 72.5% | 87.5% | 92.5% | 77.5% | 77.5% | 95% | 85% | 72.5% | 85% | 97.5% | 84.58%
Yuki Tanaka | 24 | 87.5% | 83.3% | 83.3% | 83.3% | 158.3% | 79.2% | 75% | 83.3% | 95.8% | 75% | 75% | 75% | 158.3% | 87.83%
Portfolio avg utilisation |  |  |  | 85.94%
Resources with a peak week over 100% |  |  |  | 4
Highest peak on the bench |  |  |  | 158.3%

## Defect Log
Portfolio & Resourcing Defect Log
What the PMO Analyst catches. Every defect carries a quantified consequence.
ID | Type | What was found | Severity | Quantified consequence & action | Status
P-01 | Portfolio — status | Insurance Claims Automation reported COST GREEN by the PM, but forecast at completion is 20.5% over budget. | High | $96,502 over. YTD spend was only +2.7% — the overrun sits entirely in $86,500 of committed contractor extensions the status report ignored. Escalated; recovery plan and contingency request raised. | Resolved
P-02 | Portfolio — status | Retail Bank Mobile App reported GREEN; computed AMBER (6.9% over) with 2 milestones already slipped. | Medium | $24,227 over. Reported position corrected at portfolio board; PM coached on including committed costs. | Resolved
P-03 | Portfolio — schedule | Payments Fraud Model: both remaining milestones slipped twice; production deploy now forecast Jan 2027 — outside the contract year. | High | 42-day slip. Revenue recognition moves to the next financial year. Flagged to Finance and Commercial. | Open
P-04 | Portfolio — benefits | Benefit BEN-07 (branch call volume −10%) quietly dropped in month 4. Never formally closed or re-baselined. | Medium | A promised benefit disappeared with no decision record. Business case no longer matches what will be delivered. Formal closure raised to the sponsor. | Open
P-05 | Portfolio — cost | Wealth Platform running 6% UNDER budget — read as a saving, actually a symptom of slipped delivery. | Medium | Underspend tracks a 4-week milestone slip, not efficiency. Cutover now at risk. Reframed at the board as a schedule issue, not a saving. | Resolved
R-01 | Resourcing | Priya Nair (Senior Dev) booked 56h vs 40h capacity = 140% for 3 consecutive weeks across 3 projects. | High | Burnout risk + 2 fixed-price deadlines at risk. Rebalanced 20h to Daniel Kim; capped at 100%. | Resolved
R-02 | Resourcing | Ravi Menon (32h part-time contract) booked to 40h = 125% for 2 weeks. | High | Contract breach + quality risk. Reduced to 32h; surplus BA demand redistributed. | Resolved
R-03 | Resourcing | Skill mismatch — UX Designer allocated to a data-migration task. | Medium | Rework risk. Reassigned to the Data Migration Specialist. | Resolved
R-04 | Resourcing | Ghost resource: allocation against Resource ID R-3099, not in the resource master. | Medium | 30h of real work shown as covered by a person who doesn't exist. Removed and reassigned. | Resolved
R-05 | Resourcing | 3 allocations left 'Tentative' — never confirmed. | Medium | ~60h of capacity blocked but uncommitted. Power Automate flow now chases tentatives older than 5 days. | Resolved
R-06 | Resourcing | A confirmed allocation posted with blank Booked Hours. | Low | Understated a resource's true load and masked their real utilisation. Corrected. | Resolved
R-07 | Resourcing | Duplicate allocation (same resource/project/week) inflated a week to 158%. | Medium | Double-counted capacity and triggered a false over-allocation alert. De-duplicated. | Resolved

## RAID Log
Portfolio RAID Log
Risks · Assumptions · Issues · Dependencies across the book of work.
ID | Type | Description | Owner | Impact | Mitigation / Response | Status | Raised
I-001 | Issue | Portfolio margin forecast to erode from 26.0% to 15.6% — $228K of unplanned cost. | Delivery Director | High | Driven by committed costs on 4 projects. Recovery plans requested from each PM; contingency drawdown paper to the board. | Open | 2026-08-31
I-002 | Issue | 3 of 6 projects reported Green by their PM but compute Amber or Red once committed costs are included. | PCO | High | Reporting standard changed: committed costs now mandatory in every project status. Portfolio dashboard computes RAG independently of PM self-report. | Resolved | 2026-08-31
I-003 | Issue | Senior developer over-allocated to 140% across 2 fixed-price go-lives. | Resourcing Manager | High | Rebalanced within the bench; capped at 100%. See R-01. | Resolved | 2026-06-15
R-001 | Risk | Only 2 senior developers on the bench for 6 projects — single point of failure. | Delivery Director | High | Cross-skilling plan for 2 mid-level developers; contractor pre-approved as surge cover. | Open | 2026-02-20
R-002 | Risk | Payments Fraud deploy forecast into Jan 2027 — revenue recognition slips a financial year. | Finance Business Partner | High | Flagged to Finance and Commercial; recovery options under review. | Open | 2026-08-14
R-003 | Risk | Poor allocation data quality hides true capacity. | PCO | Medium | Weekly data-quality check; automated chase on unconfirmed bookings. See R-04..R-07. | Mitigated | 2026-03-01
A-001 | Assumption | Contracted capacity in the resource master is accurate, including part-timers. | Resourcing Manager | Medium | Verified against HR contracts at kickoff; re-checked quarterly. | Open | 2026-02-02
D-001 | Dependency | Portfolio reporting depends on all 6 PMs submitting status by Wednesday 12:00. | Project Managers | High | Built into the reporting cadence; late submissions escalated to the Delivery Director. | Open | 2026-02-05

## Decision Log
Decision Log
What was decided, by whom, and why.
ID | Date | Decision | Decided by | Rationale
DEC-01 | 2026-08-31 | Report the portfolio AMBER despite 5 of 6 projects being reported Green or Amber by their PMs. | Delivery Director / PCO | Every project looked acceptable on year-to-date spend. Once $177K of committed cost was included, forecast margin fell from 26.0% to 15.6%. Reporting the PMs' aggregated view would have been accurate to what was submitted and completely misleading about where the portfolio lands.
DEC-02 | 2026-08-31 | Change the reporting standard: committed cost is now mandatory in every project status submission, and the portfolio RAG is computed centrally, not self-reported. | Delivery Director | Three PMs reported Green on projects forecasting over budget — not dishonesty, but a status template that only asked for spend to date. Fix the template, not the people.
DEC-03 | 2026-06-15 | Cap the over-allocated senior developer at 100% and move 20h/wk to a mid-level developer, accepting a minor slip on a lower-priority T&M project. | Delivery Director / PCO | A developer at 140% for three weeks will either burn out or ship defects. Both cost more than a small slip on the least critical project.
DEC-04 | 2026-08-14 | Escalate the Payments Fraud go-live slip to Finance rather than absorb it in the delivery plan. | PCO | The deploy now forecasts into January 2027, which moves revenue recognition into the next financial year. That is a Finance decision, not a delivery one.

## Governance Standards
Portfolio Governance Standards
The cadence, thresholds and data rules the PMO runs to. This is the operating manual, not a report.
REPORTING CADENCE
Forum | Frequency | Attendees | Input due | Output
Project status submission | Weekly, Wed 12:00 | All 6 PMs | Wed 12:00 | Status per project incl. committed cost
Resource Review Board | Weekly, Thu 10:00 | Resourcing Mgr, PMs, PCO | Wed EOD | Allocation changes, over-allocation cleared
Portfolio Board | Monthly, 1st Tue | Delivery Director, Finance, PMs | Prior Fri | Portfolio dashboard, decisions, escalations
Benefits review | Quarterly | Sponsor, Business owners | 2 wks prior | Benefits register updated and re-baselined
RAG THRESHOLDS — computed, not self-assessed
Measure | Green | Amber | Red
Cost variance at completion | Within −2% of budget | −2% to −10% | Worse than −10%
Milestone slip | ≤5 days | 6–20 days | Over 20 days
Resource utilisation | 75–85% | 85–90% or 60–75% | Over 90% or under 60%
Benefit tracking | On target | Within 25% of target | Missed or dropped
DATA QUALITY RULES
Rule | Why | Check frequency
Committed cost must be included in every status | Spend to date alone hides forecast overruns — this is how 3 projects reported Green while forecasting over | Weekly
No resource booked above 100% of contracted capacity | Sustained over-booking causes burnout, attrition and defects | Weekly
Tentative bookings older than 5 days are chased automatically | Unconfirmed holds block capacity that is actually available | Automated, daily
Every allocation must map to a resource in the master | Ghost resources create phantom capacity | Weekly
A benefit may only be removed by a logged decision | Benefits quietly dropped leave the business case unmatched to delivery | Quarterly

## Portfolio Status Report
Portfolio Status Report
Meridian Digital Consulting · period ending 31 Aug 2026 · for the monthly Portfolio Board
Overall | AMBER
Cost | AMBER
Schedule | AMBER
Resourcing | GREEN
Benefits | AMBER
Headline
• Five of six projects were submitted Green or Amber by their PMs. Computed centrally with committed cost included, three of those are Amber or Red.
• Portfolio margin is forecast to erode from 26.0% to 15.6% — $228,477 of unplanned cost against $2.215M of contracted revenue.
• Reporting the aggregated PM view would have been accurate to what was submitted, and misleading about where this portfolio lands.
Cost position
• Cost budget $1,640,000 · actual to date $1,448,626 · committed $177,000 · forecast at completion $1,868,477.
• Worst variance: Insurance Claims Automation — +2.7% on year-to-date spend, but 20.5% ($96,502) over at completion once contractor extensions are counted.
• Wealth Platform is 6% under budget — this is a slipped-delivery symptom, not a saving. Reframed as a schedule issue.
Delivery
• 7 milestones at risk across the portfolio; worst slip 42 days.
• Payments Fraud production deploy now forecasts January 2027 — outside the contract year. Escalated to Finance (R-002).
Resourcing
• Portfolio utilisation averages 86%. Peak weekly bookings reached 140% on one senior developer — now rebalanced and capped at 100%.
• Seven allocation data defects cleared, surfacing ~60 hours of capacity the PMO could not previously see.
Decisions required from the Board
• APPROVE the revised reporting standard: committed cost mandatory in every status; portfolio RAG computed centrally, not self-reported (DEC-02).
• APPROVE cross-skilling of 2 mid-level developers to remove the senior-developer single point of failure (R-001).
• NOTE the Payments Fraud revenue-recognition slip into FY2027 and confirm the Finance treatment.